## Dev Dashboard (hidden)
DM Scope | InScope
WorkStream | RICEFW ID | Object Name/Description | Data Objects by Workstream
MD | CHS4_C_882 | Sites and DCs | DM Scope | InScope
| CHS4_C_883 | Site Characteristic
| CHS4_C_884 | Site Class | Row Labels | Count of RICEFW ID
| CHS4_C_886 | Material Group | MD | 9
| CHS4_C_927 | Site Classification | O2C | 2
| CHS4_LSMW12 | Season Master creation | P2P | 11
| CHS4_LSMW08 | Season date upload | R2R | 15
| CHS4_LSMW09 | Add Season BU (MARC-ZZLABOR) update to this list | RET | 7
| CHS4_LSMW07 | Commodity code upload | Grand Total | 44
O2C | CHS4_C_896 | Material listing CHS4_C_896
| CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions)
P2P | CHS4_C_887 | Material Master (CHS4_C_887)
| CHS4_C_888 | Material Master - extend existing record by new org levels (CHS4_C_888)
| CHS4_C_902 | MM - Purchasing info record with conditions | Intial Review Status with Workstream
| CHS4_C_903 | Condition record for pricing in purchasing (restricted) | DM Scope | InScope
| CHS4_C_905 | Material inventory balance (AFS)
| CHS4_MAN05 | Fabric content | Count of RICEFW ID | Column Labels
| CHS4_MAN06 | Franchise | Row Labels | Completed | Grand Total
| CHS4_LSMW01 | Program to update UPC number for materials | MD | 9 | 9
| CHS4_LSMW10 | Info Records for material group (manual) | O2C | 2 | 2
| CHS4_LSMW11 | 37 ZAWA materials,2 NLAG materials, 1 VERP (manual) (Materials Ext) | P2P | 11 | 11
| CHS4_LSMW13 | UPC upload for Non-licensing product | R2R | 15 | 15
R2R | CHS4_C_870 | Bank Master | RET | 7 | 7
| CHS4_C_871 | CO - Profit center | Grand Total | 44 | 44
| CHS4_C_872 | CO - Cost center
| CHS4_C_873 | FI - Accounts payable open item
| CHS4_C_874 | FI - Accounts receivable open item
| CHS4_C_875 | FI - G/L account
| CHS4_C_876 | FI - G/L account balance and open/line item | Load Method
| CHS4_C_878 | Fixed asset (incl. balances and transactions) | DM Scope | InScope
| CHS4_C_879 | Fixed asset - Master data
| CHS4_C_880 | CO - Internal order | Row Labels | Count of RICEFW ID
| CHS4_C_881 | Customer - extend existing record by credit management data | DMC | 24
| CHS4_MAN04 | PC Hierarchy - Manual | LSMW | 1
| CHS4_MAN03 | Cost Center Hierarchy - Manual | Manual | 5
| CHS4_MAN01 | Exchange Rates - Manual CH | LSMW and DMC | 1
| CHS4_MAN02 | ALL - TVARVC entries | Custom prog. | 3
RET | CHS4_C_864 | Convert AFS ECC BP to S4 BP | Mass | 1
| CHS4_C_867 | Convert Vision Sites to S4 BP | Standard Prog | 1
| CHS4_C_893 | Customer (All Views and contact persons) | Interface | 5
| CHS4_C_895 | Customer - extend existing record by new org levels | TR | 2
| CHS4_C_899 | Supplier(All Views) | Custom Prog | 1
| CHS4_C_901 | Supplier - extend existing record by new org levels | Grand Total | 44
| CHS4_LSMW05 | Assortment Creation

## SIT1 Load Count Daily
DM Scope | InScope
Row Labels | Count of RICEFW ID
2025-07-01 | 3
2025-07-02 | 2
2025-07-03 | 1
2025-07-07 | 2
2025-07-08 | 2
2025-07-09 | 1
2025-07-10 | 4
2025-07-11 | 3
2025-07-14 | 4
2025-07-15 | 5
2025-07-16 | 3
2025-07-18 | 1
2025-07-21 | 5
2025-07-22 | 5
2025-07-23 | 3
2025-07-24 | 3
2025-07-25 | 4
2025-07-28 | 3
2025-07-29 | 2
Grand Total | 56

## loadingsttaus
|  | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6
DM Scope | InScope
Row Labels | Count of 1. Extract Status
1 - Not Started | 50
3 - Done | 6
Grand Total | 56
Not Started % | 89.29%
Done % | 11%
In progress %
Total % | 100%
DM Scope | InScope
Row Labels | Count of 2. Preload Validation Status
1 - Not Started | 56
Grand Total | 56
Not Started % | 100%
Done %
In progress %
Total % | 100%
DM Scope | InScope
Row Labels | Count of 3. Simulation Status
1 - Not Started | 56
Grand Total | 56
Not Started % | 100%
Done %
In progress %
Total % | 100%
DM Scope | InScope
Row Labels | Count of 4. Data Load Status
1 - Not Started | 56
Grand Total | 56
Not Started % | 100%
Done %
In progress %
Total % | 100%
DM Scope | InScope
Row Labels | Count of 5. Post Load Validation Status
1 - Not Started | 56
Grand Total | 56
Not Started % | 100%
Done %
In progress %
Total % | 100%

## formula (hidden)
Planned Loading Date | load | week in year | month in year | week in month |  |  |  | =WEEKNUM(B2,2)-WEEKNUM(DATE(YEAR(B2),month(b2),1),2)+1
2025-07-01 | 1 | 27 | 7 | 1 | 2025 | 2025-07-01 | 27 | 1 | TRUE | CALCAULTE WEEK OF A MONTH | =WEEKNUM(M2,2)-WEEKNUM(DATE(YEAR(M2),MONTH(M2),1),2)+1
2025-07-01 | 1 | 27 | 7 | 1 |  | 2025-07-01 | 27 | 1 | TRUE
2025-07-01 | 1 | 27 | 7 | 1 |  | 2025-07-01 | 27 | 1 | TRUE
2025-07-02 | 1 | 27 | 7 | 1 |  | 2025-07-01 | 27 | 1 | TRUE
2025-07-02 | 1 | 27 | 7 | 1 |  | 2025-07-01 | 27 | 1 | TRUE
2025-07-03 | 1 | 27 | 7 | 1 |  | 2025-07-01 | 27 | 1 | TRUE
2025-07-07 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-07 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-08 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-08 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-09 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-14 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-10 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-10 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-14 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-14 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-11 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-11 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-15 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-15 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-15 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-15 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-16 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-21 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-21 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-22 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-28 | 1 | 31 | 7 | 5 |  | 2025-07-01 | 27 | 5 | TRUE
2025-07-28 | 1 | 31 | 7 | 5 |  | 2025-07-01 | 27 | 5 | TRUE
2025-07-21 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-11 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-22 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-22 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-15 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-22 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-16 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-10 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-10 | 1 | 28 | 7 | 2 |  | 2025-07-01 | 27 | 2 | TRUE
2025-07-14 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-16 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-18 | 1 | 29 | 7 | 3 |  | 2025-07-01 | 27 | 3 | TRUE
2025-07-21 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-21 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-29 | 1 | 31 | 7 | 5 |  | 2025-07-01 | 27 | 5 | TRUE
2025-07-25 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-25 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-28 | 1 | 31 | 7 | 5 |  | 2025-07-01 | 27 | 5 | TRUE
2025-07-25 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-23 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-23 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-23 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-29 | 1 | 31 | 7 | 5 |  | 2025-07-01 | 27 | 5 | TRUE
2025-07-24 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-24 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-24 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-07-22 | 1 | 30 | 7 | 4 |  | 2025-07-01 | 27 | 4 | TRUE
2025-08-15 | 1 | 33 | 8 | 3 |  | 2025-08-01 | 31 | 3 | TRUE
|  | 1 | 1 | 1 |  | 1899-12-31 | 1 | 1 | TRUE
Formulas:
week in year = WEEKNUM([Planned Loading Date],2)
week in month = [week in year]-WEEKNUM(DATE(YEAR([Planned Loading Date]),[month in year],1),2)+1

## Weekly Load Status
Month | July
Load Method | (Multiple Items)
Extraction_Status | Column Labels
Weeks | 1 - Not Started | 2 - In progress | 3 - Done | Grand Total
1 |  |  | 4 | 4
2 | 9 |  | 1 | 10
3 | 12 |  |  | 12
4 | 15 | 6 |  | 21
5 | 3 | 1 |  | 4
Grand Total | 39 | 7 | 5 | 51
Not Started | 76.47%
In progress | 13.73%
Done | 9.804%
Total | 100%
Month | July
Load Method | (Multiple Items)
Preload Status | Column Labels
Weeks | 1 - Not Started | 3 - Done | 2 - In progress | Grand Total
1 | 2 | 2 |  | 4
2 | 3 | 6 | 1 | 10
3 | 11 | 1 |  | 12
4 | 17 |  | 4 | 21
5 | 2 |  | 2 | 4
Grand Total | 35 | 9 | 7 | 51
Not Started | 68.63%
In progress | 13.73%
Done | 17.65%
Total | 100%
Month | July
Load Method | (Multiple Items)
Simulation Status | Column Labels
Weeks | 1 - Not Started | 2 - In progress | 3 - Done | Grand Total
1 | 2 | 2 |  | 4
2 | 3 | 6 | 1 | 10
3 | 11 | 1 |  | 12
4 | 17 |  | 4 | 21
5 | 2 |  | 2 | 4
Grand Total | 35 | 9 | 7 | 51
Not Started | 68.63%
In progress | 17.65%
Done | 13.73%
Total | 100%
Month | July
Load Method | (Multiple Items)
Data Load Status | Column Labels
Weeks | 1 - Not Started | 2 - In progress | 3 - Done | Grand Total
1 | 4 |  |  | 4
2 | 4 | 6 |  | 10
3 | 8 | 2 | 2 | 12
4 | 21 |  |  | 21
5 | 4 |  |  | 4
Grand Total | 41 | 8 | 2 | 51
Not Started | 80.39%
In progress | 15.69%
Done | 3.922%
Total | 100%
Month | July
Load Method | (All)
Post Load Validation | Column Labels
Weeks | 1 - Not Started | 3 - Done | 2 - In progress | Grand Total
1 | 3 |  | 3 | 6
2 | 7 | 5 |  | 12
3 | 18 |  |  | 18
4 | 26 |  |  | 26
5 | 5 |  |  | 5
Grand Total | 59 | 5 | 3 | 67
Not Started | 88.06%
In progress | 4.478%
Done | 7.463%
Total | 100%

## Dev Tracker
WorkStream | RICEFW ID | Object Name/Description | DMCTemplate WalkthruStatus | DMC Walkthrough – Completion Date | DM Scope | Object type | Load Seq# | Parallel Load Possible | Predecessor | Planned Collection Date | Actual Collection Date | Planned Loading Date | Month | Week of Loading Month | Actual Loading Date | Extraction Plan | Extract Program Status | Extraction Status | Load File Status | Load Status | Post Load Validaton | Custom/Standard Program | Load Method | DM Primary Resource | Workstream Lead | Business Lead | Sprint | Initial Functional Review Status | Technical Specification Status | Technical Unit Testing(TUT) Status | DMC Project Name | Additional Comments | Additional Fields | Manual/LSMW Dataload | TCODE | TABLE | No. of Records | Notes | WorkStream | Object Name | Load Type | Load Program Status | Data Extract Needed | 1. Extract Status | 1. Extract Prepare Record Count | 2. Preload Validation Status | 3. Simulation Status | 3. Simulation Record Count | 4. Data Load Status | 4. Data Load Record Count | 5. Post Load Validation Status | 5. Post Load Validation Record Count | Mock1 Status | Mock1 % Success Target 50% | DM Scope
R2R | CHS4_C_875 | FI - G/L account | Completed | May-21-2025 | InScope | MD | 1.1 | Y |  |  | 2025-06-25 | 2025-07-01 | July | 1 |  | 2025-06-10 | Complete |  |  |  | 2025-07-02 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_875_GL_M0A | [6 empty] | Complete | R2R | FI - G/L account | DMC | 3 - Done | Y | 3 - Done | 8561 | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 2 - In progress |  | InScope
R2R | CHS4_MAN04 | PC Hierarchy - Manual | Manual |  | InScope | MD | 1.2 | N |  |  | 2025-06-25 | 2025-07-01 | July | 1 |  | 2025-06-12 | N/A |  |  |  | 2025-07-02 |  | Manual | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Manual activity/No extract expected | R2R | PC Hierarchy - Manual | Manual | 1 - Not Started | N | 3 - Done |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_MAN03 | Cost Center Hierarchy - Manual | Manual |  | InScope | MD | 1.3 | Y |  |  | 2025-06-25 | 2025-07-01 | July | 1 |  | 2025-06-12 | N/A |  |  |  | 2025-07-02 |  | Manual | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Manual activity/No extract expected | R2R | Cost Center Hierarchy - Manual | Manual | 1 - Not Started | N | 3 - Done |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_C_871 | CO - Profit center | Completed | May-21-2025 | InScope | MD | 1.4 | N | CHS4_MAN04 |  | 2025-06-25 | 2025-07-02 | July | 1 |  | 2025-06-11 | Complete |  |  |  | 2025-07-03 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_871_Profit center_M0S | [6 empty] | Complete | R2R | CO - Profit center | DMC | 3 - Done | Y | 3 - Done | 926 | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 2 - In progress |  | 2 - In progress |  | InScope
R2R | CHS4_C_872 | CO - Cost center | Completed | May-21-2025 | InScope | MD | 1.5 | N | CHS4_MAN03,CHS4_C_871 |  | 2025-06-25 | 2025-07-02 | July | 1 |  | 2025-06-10 | Complete |  |  |  | 2025-07-03 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_872_Cost center | [6 empty] | Complete | R2R | CO - Cost center | DMC | 3 - Done | Y | 3 - Done | 804 | 3 - Done | 2 - In progress |  | 1 - Not Started |  | 2 - In progress |  | 2 - In progress |  | InScope
R2R | CHS4_C_870 | Bank Master | Completed | May-21-2025 | InScope | MD | 1.6 | Y |  |  | 2025-06-25 | 2025-07-03 | July | 1 |  | 2025-06-09 | Complete |  |  |  | 2025-07-07 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_870_Bank Master_M0R | [6 empty] | Complete | R2R | Bank Master | DMC | 3 - Done | Y | 3 - Done | 2459 | 3 - Done | 2 - In progress |  | 1 - Not Started |  | 2 - In progress |  | 2 - In progress |  | InScope
MD | CHS4_C_883 | Site Characteristic | Completed |  | InScope | MD | 2.1 | N | CHS4_C_884 |  | 2025-07-01 | 2025-07-07 | July | 2 |  | 2025-06-12 | Complete |  |  |  | 2025-07-08 |  | DMC | Sona Das | Vishnu |  | Sprint1 | Completed |  |  | PRJ_RET_CHS4_C_883_Characteristic_M10 | [6 empty] | Arlan provided the data | MD | Site Characteristic | DMC | 3 - Done | Y | 3 - Done | 40 | 3 - Done | 2 - In progress |  | 1 - Not Started |  | 3 - Done |  | 2 - In progress |  | InScope
MD | CHS4_C_884 | Site Class | Manual |  | InScope | MD | 2.1 | Y |  |  | 2025-07-01 | 2025-07-07 | July | 2 |  | 2025-06-12 | Complete |  |  |  | 2025-07-08 |  | Manual | Sona Das | Vishnu |  | Sprint1 | Completed |  |  |  | Only one class Vishnu confirmed ,it will be created from there side. |  | complete |  |  |  | Manual activity/No extract expected | MD | Site Class | Manual | 1 - Not Started | N | 3 - Done | 1 | 3 - Done | 2 - In progress |  | 2 - In progress |  | 3 - Done |  | 2 - In progress |  | InScope
RET | CHS4_C_867 | Convert Vision Sites to S4 BP | Completed | May-28-2025 | InScope | MD | 2.2 | N | CHS4_C_871 |  | 2025-07-02 | 2025-07-08 | July | 2 |  | 2025-06-12 | [6 empty] | DMC | Sona Das | Vishnu/Xiao |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_867_BP_VisionSites_M1F | [6 empty] | Site/Customer/Supplier data from Vision | RET | Convert Vision Sites to S4 BP | DMC | 3 - Done | Y | 1 - Not Started |  | 3 - Done | 2 - In progress |  | 2 - In progress |  | 3 - Done |  | 1 - Not Started |  | InScope
MD | CHS4_C_882 | Sites and DCs | Completed |  | InScope | MD | 2.2 | Y | CHS4_MAN04 |  | 2025-07-02 | 2025-07-08 | July | 2 |  | 2025-06-12 |  |  |  |  | 2025-07-09 |  | LSMW and DMC | Sona Das | Vishnu |  | Sprint1 | Completed |  |  | PRJ_RET_CHS4_C_882_Site_DC |  |  | complete |  |  |  | Need to discuss further with Manoj | MD | Sites and DCs | LSMW and DMC | 1 - Not Started | Y | 1 - Not Started |  | 3 - Done | 2 - In progress |  | 2 - In progress |  | 3 - Done |  | 1 - Not Started |  | InScope
MD | CHS4_C_927 | Site Classification | Completed | June-12-2025 | InScope | MD | 2.3 | N | CHS4_C_882, CHS4_C_883, CHS4_C_884 |  | 2025-07-03 | 2025-07-09 | July | 2 |  | 2025-06-12 |  |  |  |  | 2025-07-10 |  | DMC | Manoj | Vishnu |  | Sprint1 | Completed |  |  | N/A | New object needed for site classification confirmed by Vishnu on 12-05-2025 | [5 empty] | Arlan to Provide the data | MD | Site Classification | DMC | 3 - Done | Y | 1 - Not Started |  | 3 - Done | 2 - In progress |  | 2 - In progress |  | 3 - Done |  | 1 - Not Started |  | InScope
R2R | CHS4_MAN01 | Exchange Rates - Manual CH | Manual |  | InScope | MD | 2.4 | Y |  |  | 2025-07-08 | 2025-07-14 | July | 3 |  | 2025-06-11 |  |  |  |  | 2025-07-15 |  | Manual | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Manual activity/Ram | R2R | Exchange Rates - Manual CH | Manual | 1 - Not Started | Y | 1 - Not Started |  | 3 - Done | 2 - In progress |  | 2 - In progress |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_C_893 | Customer (All Views and contact persons) | Completed | May-28-2025 | InScope | MD | 2.5 | N | CHS4_C_875, CHS4_C_870 |  | 2025-07-03 | 2025-07-10 | July | 2 |  | 2025-06-16 |  |  |  |  | 2025-07-11 |  | DMC | Anu | Xiao Fu |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_893_Customer_M1A |  | KNA1,KNVV, | [5 empty] | RET | Customer (All Views and contact persons) | DMC | 3 - Done | Y | 1 - Not Started |  | 3 - Done | 2 - In progress |  | 2 - In progress |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_C_899 | Supplier(All Views) | Completed | May-28-2025 | InScope | MD | 2.6 | N | CHS4_C_875, CHS4_C_870 |  | 2025-07-03 | 2025-07-10 | July | 2 |  | 2025-06-17 |  |  |  |  | 2025-07-11 |  | DMC | Sharon | Xiao Fu |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_899_Supplier_M0H |  | Transportation Chain | [5 empty] | RET | Supplier(All Views) | DMC | 3 - Done | Y | 1 - Not Started |  | 3 - Done | 2 - In progress |  | 2 - In progress |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_C_881 | Customer - extend existing record by credit management data | Completed | May-28-2025 | InScope | MD | 2.7 | Y |  |  | 2025-07-08 | 2025-07-14 | July | 3 | [6 empty] | 2025-07-15 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_881_Customer_extend | [7 empty] | R2R | Customer - extend existing record by credit management data | DMC | 3 - Done | Y | 1 - Not Started |  | 3 - Done | 2 - In progress |  | 2 - In progress |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_C_880 | CO - Internal order | Completed | May-28-2025 | InScope | MD | 2.8 | N | CHS4_C_872 |  | 2025-07-08 | 2025-07-14 | July | 3 |  |  | Complete |  |  |  | 2025-07-17 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_880_Internal order_M0D | [6 empty] | Complete | R2R | CO - Internal order | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 2 - In progress |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_MAN02 | ALL - TVARVC entries | Manual |  | InScope | MD | 3.1 | Y |  |  | 2025-07-07 | 2025-07-11 | July | 2 | [6 empty] | 2025-07-14 |  | TR | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | N/A | [7 empty] | R2R | ALL - TVARVC entries | TR | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 2 - In progress |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_C_864 | Convert AFS ECC BP to S4 BP | Completed | May-28-2025 | InScope | MD | 3.2 | N | CHS4_C_882 |  | 2025-07-07 | 2025-07-11 | July | 2 | [6 empty] | 2025-07-14 |  | DMC | Sona Das | Vishnu/Xiao |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_864_BP_ECC_M05 | [6 empty] | Collection management data ->R2R/UDM_SPECIALIST | RET | Convert AFS ECC BP to S4 BP | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 2 - In progress |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_MAN05 | Fabric content | Manual |  | InScope | MD | 3.3 | Y |  |  | 2025-07-09 | 2025-07-15 | July | 3 |  |  | Complete |  |  |  | 2025-07-18 |  | LSMW | Sharon | Shabu George |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Complete | P2P | Fabric content | LSMW | 3 - Done | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_MAN06 | Franchise | Manual |  | InScope | MD | 3.4 | Y |  |  | 2025-07-09 | 2025-07-15 | July | 3 |  |  | Complete |  |  |  | 2025-07-18 |  | TR | Sharon | Shabu George |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Complete | P2P | Franchise | TR | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | InScope
MD | CHS4_LSMW12 | Season Master creation | In progress |  | InScope | MD | 3.5 | Y |  |  | 2025-07-09 | 2025-07-15 | July | 3 |  |  | Complete |  |  |  | 2025-07-18 |  | Manual | Sona Das | Koustubh |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Complete | MD | Season Master creation | Manual | 1 - Not Started | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | InScope
OTC | CHS4_LSMW08 | Season date upload | In progress |  | InScope | MD | 3.6 | N | CHS4_LSMW08 |  | 2025-07-09 | 2025-07-15 | July | 3 |  |  | Complete |  |  |  | 2025-07-18 | ZSEASONS_UPLOAD | Custom prog. | Sona Das | Vishnu |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Complete | OTC | Season date upload | Custom prog. | 2 - In progress | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | InScope
MD | CHS4_LSMW09 | Add Season BU (MARC-ZZLABOR) update to this list | In progress |  | InScope | MD | 3.7 | N | CHS4_C_887, CHS4_C_882 |  | 2025-07-10 | 2025-07-16 | July | 3 |  |  | Complete |  |  |  | 2025-07-19 |  | Mass | Sona Das | Vishnu |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Arlan provided the data | MD | Add Season BU (MARC-ZZLABOR) update to this list | Mass | 1 - Not Started | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_C_873 | FI - Accounts payable open item | Completed | May-28-2025 | InScope | TD | 4.1 | N | CHS4_C_871, CHS4_C_875, CHS4_C_899 |  | 2025-07-15 | 2025-07-21 | July | 4 | [6 empty] | 2025-07-24 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_873_AP | [7 empty] | R2R | FI - Accounts payable open item | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_C_874 | FI - Accounts receivable open item | Completed | May-28-2025 | InScope | TD | 4.2 | N | CHS4_C_871, CHS4_C_875, CHS4_C_893 |  | 2025-07-15 | 2025-07-21 | July | 4 | [6 empty] | 2025-07-24 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_874_AR | [7 empty] | R2R | FI - Accounts receivable open item | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_C_876 | FI - G/L account balance and open/line item | Completed | May-28-2025 | InScope | TD | 4.3 | N | CHS4_C_871, CHS4_C_875, CHS4_C_872 |  | 2025-07-16 | 2025-07-22 | July | 4 | [6 empty] | 2025-07-25 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_876_GL_Openitem_Balance_M0B | [7 empty] | R2R | FI - G/L account balance and open/line item | DMC | 3 - Done | Y | 1 - Not Started |  | 2 - In progress | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_C_879 | Fixed asset - Master data | Completed | May-28-2025 | InScope | MD | 4.4 | N | CHS4_C_871, CHS4_C_872 |  | 2025-07-24 | 2025-07-28 | July | 5 | [6 empty] | 2025-07-31 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_879_Asset_MD_ | [6 empty] | Connect with Suraj | R2R | Fixed asset - Master data | DMC | 3 - Done | Y | 1 - Not Started |  | 2 - In progress | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_C_878 | Fixed asset (incl. balances and transactions) | Completed | May-28-2025 | InScope | TD | 4.5 | N | CHS4_C_871, CHS4_C_875 |  | 2025-07-24 | 2025-07-28 | July | 5 | [6 empty] | 2025-07-31 |  | DMC | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | PRJ_R2R_CHS4_C_878_Asset_TD_MOC | [6 empty] | Connect with Suraj | R2R | Fixed asset (incl. balances and transactions) | DMC | 3 - Done | Y | 1 - Not Started |  | 2 - In progress | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_LSMW05 | Assortment Creation | In progress |  | InScope | MD | 4.6 | N | CHS4_C_882, CHS4_C_886 |  | 2025-07-15 | 2025-07-21 | July | 4 | [6 empty] | 2025-07-24 |  | DMC custom | Anu | Koustubh |  | Sprint1 | Completed |  |  | N/A | [6 empty] | No extract needed? | RET | Assortment Creation | DMC custom | 1 - Not Started | Y | 1 - Not Started |  | 2 - In progress | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
MD | CHS4_C_886 | Material Group | Completed | June-12-2025 | InScope | MD | 5.1 | Y |  |  | 2025-07-03 | 2025-07-11 | July | 2 |  |  | Complete |  |  |  | 2025-07-14 |  | DMC | Sona Das | Koustubh |  | Sprint1 | Completed |  |  | PRJ_RET_CHS4_C_886_Merchandise Catergories_M13 | [6 empty] | Complete | MD | Material Group | DMC | 3 - Done | Y | 1 - Not Started |  | 2 - In progress | 3 - Done |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_LSMW01 | Program to update UPC number for materials | In progress |  | InScope | MD | 5.11 | N | CHS4_C_887 |  | 2025-07-15 | 2025-07-22 | July | 4 |  |  | Complete |  |  |  | 2025-07-25 | ZPLM_LICUPC_UPLOAD | Standard Prog | Sharon | Koustubh |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Complete | P2P | Program to update UPC number for materials | Standard Prog | 3 - Done | Y | 1 - Not Started |  | 2 - In progress | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_LSMW10 | Info Records for material group (manual) | In progress |  | InScope | MD | 5.12 | N | CHS4_C_899 |  | 2025-07-15 | 2025-07-22 | July | 4 |  |  | Complete |  |  |  | 2025-07-25 |  | DMC | Sharon | Koustubh |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Complete | P2P | Info Records for material group (manual) | DMC | 3 - Done | Y | 1 - Not Started |  | 2 - In progress | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_LSMW11 | 37 ZAWA materials,2 NLAG materials, 1 VERP (manual) (Materials Ext) | In progress |  | InScope | MD | 5.13 | N | CHS4_C_882, CHS4_C_871, CHS4_C_899 |  | 2025-07-09 | 2025-07-15 | July | 3 | [6 empty] | 2025-07-18 |  | DMC | Sharon | Koustubh |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Zstyles: X from 2018, Z all ==> ZAWA/Check with Kausthob | P2P | 37 ZAWA materials,2 NLAG materials, 1 VERP (manual) (Materials Ext) | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_LSMW13 | UPC upload for Non-licensing product | In progress |  | InScope | MD | 5.14 | N | CHS4_C_887 |  | 2025-07-15 | 2025-07-22 | July | 4 | [6 empty] | 2025-07-25 | MASS_MEAN | Custom prog. | Sharon | Koustubh |  | Sprint1 | Completed |  |  | N/A | [6 empty] | MEAN : Non licensed | P2P | UPC upload for Non-licensing product | Custom prog. | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
MD | CHS4_LSMW07 | Commodity code upload | In progress |  | InScope | MD | 5.15 | Y |  |  | 2025-07-10 | 2025-07-16 | July | 3 |  |  | Complete |  |  |  | 2025-07-19 |  | Custom prog. | Sona Das | Vishnu |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Complete/concatenate texts | MD | Commodity code upload | Custom prog. | 2 - In progress | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_C_895 | Customer - extend existing record by new org levels | Completed | May-28-2025 | InScope | MD | 5.2 | N | CHS4_C_893 |  | 2025-07-04 | 2025-07-10 | July | 2 |  | 2025-06-16 |  |  |  |  | 2025-07-13 |  | DMC | Anu | Xiao Fu |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_895_Customer_EXT_ORG_M1B | [7 empty] | RET | Customer - extend existing record by new org levels | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_C_901 | Supplier - extend existing record by new org levels | Completed | May-28-2025 | InScope | MD | 5.3 | N | CHS4_C_899 |  | 2025-07-04 | 2025-07-10 | July | 2 | [6 empty] | 2025-07-13 |  | DMC | Sharon | Xiao Fu |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_901_Supplier_Ext_M0J | [7 empty] | RET | Supplier - extend existing record by new org levels | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_C_887 | Material Master (CHS4_C_887) | Not Applicable |  | InScope | MD | 5.5 | N | CHS4_C_871, CHS4_C_882 |  | 2025-07-08 | 2025-07-14 | July | 3 |  |  | N/A |  |  |  | 2025-07-17 |  | Interface | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_RET_CHS4_C_887_Materials_M14 | Out of scope confimed by Koustubh on 12-05-2025 | [5 empty] | From PLM | P2P | Material Master (CHS4_C_887) | Interface | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_C_888 | Material Master - extend existing record by new org levels (CHS4_C_888) | Not Applicable |  | InScope | MD | 5.6 | N | CHS4_C_887 |  | 2025-07-10 | 2025-07-16 | July | 3 |  |  | N/A |  |  |  | 2025-07-19 |  | Interface | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_RET_CHS4_C_888_Materials_ext_M15 | Out of scope confimed by Koustubh on 12-05-2025 | [5 empty] | NA | P2P | Material Master - extend existing record by new org levels (CHS4_C_888) | Interface | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
OTC | CHS4_C_896 | Material listing CHS4_C_896 | In Progress |  | InScope | MD | 5.7 | N | CH_S4_C_887, CHS4_LSMW04 |  | 2025-07-12 | 2025-07-18 | July | 3 |  |  | N/A |  |  |  | 2025-07-21 |  | Interface | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_O2C_CHS4_C_896_Material_listingexclusion_M1C | Anil Confired on 29-05-2025 during DMC walk thru | [5 empty] | NA | OTC | Material listing CHS4_C_896 | Interface | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_C_902 | MM - Purchasing info record with conditions | Not Applicable |  | InScope | MD | 5.8 | N | CHS4_C_882, CHS4_C_887, |  | 2025-07-15 | 2025-07-21 | July | 4 |  |  | N/A |  |  |  | 2025-07-24 |  | Interface | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_P2P_CHS4_C_902_PIR_M0K | Koustubh Kashalkar confirmed during DMC walk thru date June-03-2025 | [5 empty] | From PLM | P2P | MM - Purchasing info record with conditions | Interface | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_C_903 | Condition record for pricing in purchasing (restricted) | Not Applicable |  | InScope | MD | 5.9 | N | CHS4_C_887, CHS4_C_903 |  | 2025-07-15 | 2025-07-21 | July | 4 |  |  | N/A |  |  |  | 2025-07-24 |  | Interface | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_P2P_CHS4_C_903_Condition_Price_purchase_M0L | Koustubh Kashalkar confirmed during DMC walk thru date June-03-2025 | [5 empty] | From PLM | P2P | Condition record for pricing in purchasing (restricted) | Interface | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_C_905 | Material inventory balance (AFS) | Completed | June-12-2025 | InScope | TD | 6.1 | N | CHS4_C_887, CHS4_C_882, CHS4_C_875 |  | 2025-07-23 | 2025-07-29 | July | 5 | [6 empty] | 2025-08-01 |  | DMC | Sharon | Koustubh |  | Sprint1 | Completed |  |  | PRJ_P2P_CHS4_C_905_Material_inventory_balance_M0N | [6 empty] | Need to map | P2P | Material inventory balance (AFS) | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
OTC | CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | Completed | June-02-2025 | InScope | TD | 6.11 | N | CHS4_C_882, CHS4_C_887, |  | 2025-07-19 | 2025-07-25 | July | 4 | [6 empty] | 2025-07-28 |  | DMC | Anu | Sarah |  | Sprint1 | Completed |  |  | PRJ_O2C_CHS4_C_898_Sales Order_M1E | [7 empty] | OTC | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_LSMW04 | MM - Purchase order (only open PO) ( Vision) | In progress |  | InScope | TD | 6.12 | N | CHS4_C_882, CHS4_C_887, |  | 2025-07-19 | 2025-07-25 | July | 4 | [6 empty] | 2025-07-28 |  | DMC | Sharon | Koustubh |  | Sprint1 | Completed |  |  | N/A | [7 empty] | P2P | MM - Purchase order (only open PO) ( Vision) | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
R2R | CHS4_MAN07 | ZINTINV1 | Manual |  | InScope | MD | 6.13 | N | CHS4_C_898 |  | 2025-07-22 | 2025-07-28 | July | 5 | [6 empty] | 2025-07-31 |  | Manual | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | N/A | [6 empty] | Not Part of Custom table migration? | R2R | ZINTINV1 | Manual | 1 - Not Started | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_C_907 | MM - Purchase order (only open PO) (AFS) | Completed | June-02-2025 | InScope | TD | 6.2 | N | CHS4_C_882, CHS4_C_887,CHS4_C_899 |  | 2025-07-18 | 2025-07-25 | July | 4 | [6 empty] | 2025-07-28 |  | DMC | Sharon | Koustubh |  | Sprint1 | Completed |  |  | PRJ_P2P_CHS4_C_907_Purchase_order _M0G | [7 empty] | P2P | MM - Purchase order (only open PO) (AFS) | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
OTC | CHS4_C_891 | Condition record for pricing (general template) | Completed | June-02-2025 | InScope | MD | 6.3 | N | CHS4_C_887, CHS4_C_899 |  | 2025-07-17 | 2025-07-23 | July | 4 | [6 empty] | 2025-07-26 |  | DMC | Anu | Sarah |  | Sprint1 | Completed |  |  | PRJ_O2C_CHS4_C_891_Con_pricing_M18 | [7 empty] | OTC | Condition record for pricing (general template) | DMC | 3 - Done | Y | 2 - In progress |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
OTC | CHS4_C_892 | Condition record for pricing in sales (restricted) | Completed | June-02-2025 | InScope | MD | 6.4 | N | CHS4_C_887, CHS4_C_893 |  | 2025-07-17 | 2025-07-23 | July | 4 | [6 empty] | 2025-07-26 |  | DMC | Anu | Sarah |  | Sprint1 | Completed |  |  | PRJ_O2C_CHS4_C_892_Con_pricing_res_M19 | [7 empty] | OTC | Condition record for pricing in sales (restricted) | DMC | 3 - Done | Y | 2 - In progress |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_LSMW02 | Retail Pricing upload from Vision | In progress | ` | InScope | MD | 6.5 | N | CHS4_C_887, CHS4_C_882 |  | 2025-07-17 | 2025-07-23 | July | 4 | [6 empty] | 2025-07-26 |  | LSMW | Anu | Vishnu |  | Sprint1 | Completed |  |  | N/A | [7 empty] | RET | Retail Pricing upload from Vision | LSMW | 1 - Not Started | N | 2 - In progress |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_LSMW03 | Store Inventory upload from Vision | In progress |  | InScope | MD | 6.6 | N | CHS4_MAN04, CHS4_C_875 |  | 2025-07-23 | 2025-07-29 | July | 5 | [6 empty] | 2025-08-01 |  | DMC | Sharon | Vishnu |  | Sprint1 | Completed |  |  | N/A | [7 empty] | RET | Store Inventory upload from Vision | DMC | 3 - Done | Y | 2 - In progress |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
OTC | TBD | VAS Records |  |  | InScope | MD | 6.7 | N | CHS4_C_887 |  | 2025-07-18 | 2025-07-24 | July | 4 | [6 empty] | 2025-07-27 |  | Custom prog. | Anu | Anil | [9 empty] | VA03 |  |  |  | OTC | VAS Records | Custom prog. | 2 - In progress | Y | 2 - In progress |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
OTC | CHS4_C_CPR1 | Output Conditions Records |  |  | InScope | MD | 6.8 | N | CHS4_C_882, CHS4_C_887, |  | 2025-07-18 | 2025-07-24 | July | 4 | [6 empty] | 2025-07-27 |  | Custom prog. | Anu | Anil | [9 empty] | VV11 | NACH |  |  | OTC | Output Conditions Records | Custom prog. | 2 - In progress | Y | 2 - In progress |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_C_CPR2 | Output Conditions Records |  |  | InScope | MD | 6.9 | N | CHS4_C_899 |  | 2025-07-18 | 2025-07-24 | July | 4 | [6 empty] | 2025-07-27 |  | Custom prog. | Sharon | Koustubh | [13 empty] | P2P | Output Conditions Records | Custom prog. | 2 - In progress | Y | 2 - In progress |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
P2P | CHS4_C_909 | MM - Source list | Not Applicable |  | InScope | MD | 5.10 | N | CHS4_C_882, CHS4_C_887, |  | 2025-07-15 | 2025-07-22 | July | 4 | [6 empty] | 2025-07-25 |  | Interface | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_P2P_CHS4_C_909_Source list_M0O | Koustubh Kashalkar confirmed during DMC walk thru date June-03-2025 | [5 empty] | Extract from PLM | P2P | MM - Source list | Interface | 1 - Not Started | N | 2 - In progress |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
OTC | CHS4_C_897 | SD - Sales contract | Completed | June-02-2025 | InScope | TD | 6.10 | N | CHS4_C_887, CHS4_C_882 |  | 2025-07-19 | 2025-07-25 | July | 4 | [6 empty] | 2025-07-28 |  | DMC | Anu | Sarah |  | Sprint1 | Completed |  |  | PRJ_O2C_CHS4_C_897_Sales contract_M1D | [7 empty] | OTC | SD - Sales contract | DMC | 3 - Done | Y | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | InScope
RET | CHS4_C_894 | Customer - extend existing record by multiple addresses | Not Applicable | May-28-2025 | Descoped | MD | [5 empty] | 2025-07-17 | July | 3 | [8 empty] | DMC | Anu | Xiao Fu |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_894_Customer_EXT_Addrss | [7 empty] | RET | Customer - extend existing record by multiple addresses | DMC | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
RET | CHS4_C_900 | Supplier - extend existing record by multiple addresses | Not Applicable | May-28-2025 | Descoped | MD | [5 empty] | 2025-07-17 | July | 3 | [8 empty] | DMC | Sharon | Xiao Fu |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_900_Supplier_Ext_address | [7 empty] | RET | Supplier - extend existing record by multiple addresses | DMC | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
RET | CHS4_C_865 | Convert AFS ECC Customer Master to S4 BP | Completed | May-28-2025 | Descoped | MD | [5 empty] | 2025-07-18 | July | 3 | [8 empty] | DMC | Sona Das | Vishnu/Xiao |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_865_BP_Customer_M06 | [7 empty] | RET | Convert AFS ECC Customer Master to S4 BP | DMC | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
RET | CHS4_C_866 | Convert AFS ECC Vendor Master to S4 BP | Completed | May-28-2025 | Descoped | MD | [5 empty] | 2025-07-19 | July | 3 | [8 empty] | DMC | Sona Das | Vishnu/Xiao |  | Sprint1 | Completed |  |  | PRJ_MD_CHS4_C_866_BP_supplier_M07 | [7 empty] | RET | Convert AFS ECC Vendor Master to S4 BP | DMC | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
RET | CHS4_C_885 | Merchandise Hierarchy(CHS4_C_885) | Not Applicable |  | Descoped | MD | 0 |  | N |  |  | 2025-07-20 | July | 3 | [8 empty] | LSMW | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_RET_CHS4_C_885_Merchandise Hierarchy_M12 | Out of scope confimed by Koustubh on 12-05-2025.(Material heirarchy i snot used) | [6 empty] | RET | Merchandise Hierarchy(CHS4_C_885) | LSMW | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
P2P | CHS4_C_889 | Product consumption(CHS4_C_889) | 882 |  | Descoped | MD | 0 |  | N |  |  | 2025-07-21 | July | 4 | [8 empty] | LSMW | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_RET_CHS4_C_889_Product_consumption_M16 | Out of scope confimed by Koustubh on 12-05-2025 | [6 empty] | P2P | Product consumption(CHS4_C_889) | LSMW | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
OTC | CHS4_C_890 | Service product(CHS4_C_890) | Not Applicable |  | Descoped | MD | 0 |  | N |  |  | 2025-07-22 | July | 4 | [10 empty] | Koustubh |  | Sprint1 | Completed |  |  | PRJ_RET_CHS4_C_890_Service_product_M17 | Out of scope confimed by Koustubh on 12-05-2025 | [6 empty] | OTC | Service product(CHS4_C_890) | 0 | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
R2R | CHS4_C_926 | Good Will Impairment Analysis | Manual |  | Descoped | MD | [5 empty] | 2025-07-23 | July | 4 | [6 empty] | 2025-07-26 |  | Manual | Manoj | Binoj/Harshit |  | Sprint1 | Completed |  |  | N/A | [7 empty] | R2R | Good Will Impairment Analysis | Manual | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
P2P | CHS4_C_904 | Material - Forecast planning(CHS4_C_904) | Not Applicable |  | Descoped | MD | 0 |  | N |  |  | 2025-07-24 | July | 4 | [8 empty] | LSMW | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_P2P_CHS4_C_904_Material_ Forecast_ planning_M03 | confirmed by Kustubh 7th052025 | [6 empty] | P2P | Material - Forecast planning(CHS4_C_904) | LSMW | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
P2P | CHS4_C_910 | Batch unique at material and client level(CHS4_C_910) | Not Applicable |  | Descoped | MD | 0 |  | N |  |  | 2025-07-25 | July | 4 | [8 empty] | LSMW | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_P2P_CHS4_C_910_Batch_Material_M0P | confirmed by Kustubh 7th052025 (Batch is not used by cole haan) | [6 empty] | P2P | Batch unique at material and client level(CHS4_C_910) | LSMW | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
P2P | CHS4_C_910 | Batch unique at plant level(CHS4_C_910) | Not Applicable |  | Descoped | MD | 0 |  | N |  |  | 2025-07-26 | July | 4 | [8 empty] | LSMW | Manoj | Koustubh |  | Sprint1 | Completed |  |  | PRJ_P2P_CHS4_C_911_Batch_Plant_M0Q | confirmed by Kustubh 7th052025 (Batch is not used by cole haan) | [6 empty] | P2P | Batch unique at plant level(CHS4_C_910) | LSMW | 1 - Not Started | N | 1 - Not Started |  | 1 - Not Started | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | 1 - Not Started |  | Descoped
Formulas:
Actual Collection Date = +[Planned Loading Date]-6
Post Load Validaton = +[Planned Loading Date]+1
Note on AF11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Site creation using LSMW
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New object confirmed by Vishnu

## KPI
DM Scope | (Multiple Items) |  | Mock1 Status
Column Labels
| 1 - Not Started |  | 2 - In progress |  | Total Success Rate | Total Count
WorkStream | Success Rate | Count | Success Rate | Count
MD |  | 7 |  | 1 |  | 8
OTC |  | 8 |  |  |  | 8
R2R |  | 12 |  | 4 |  | 16
RET |  | 9 |  |  |  | 9
P2P |  | 15 |  |  |  | 15
Grand Total |  | 51 |  | 5 |  | 56
Extraction Status
3 - Done
2 - In progress
1 - Not Started
DM Scope | InScope
WorkStream | Column Labels
Row Labels | MD | OTC | R2R | RET | P2P | Grand Total
1 - Not Started | 7 | 8 | 12 | 9 | 15 | 51
3 - Done | 1 |  | 4 |  |  | 5
Grand Total | 8 | 8 | 16 | 9 | 15 | 56

## Mock1_data load_task_details
WorkStream | Task ID | RICEFW ID | Object Name/Description | Object type | Load Seq# | Predecessors | Task Details | Load Method | Team Responsible | Person Responsible | Email Of the Person Responsible | Start Date/Time | End Date/Time
S4: Client creation
S4: Patching and Upgrades related to DMC
S4: Users / Profiles creation
S4: IDOC / ALE / RFC setup
S4: Config/Development/Data Transport Movements
S4: LSMW Setups
|  |  | Pre-Cutover Tasks |  |  |  | User Login Tests
DMC Smoke tests
R2R Configuration Checks and NR setup
P2P Configuration Checks and NR setup
OTC Configuration Checks and NR setup
RET Configuration Checks and NR setup
R2R | 1 | CHS4_C_875 | FI - G/L account | Master Data | 1.1 |  | Main task
R2R | 2 | CHS4_C_875 | FI - G/L account | Master Data | 1.1 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-06-25 | 2025-06-26
R2R | 3 | CHS4_C_875 | FI - G/L account | Master Data | 1.1 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-06-26 | 2025-06-27
R2R | 4 | CHS4_C_875 | FI - G/L account | Master Data | 1.1 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-06-27 | 2025-06-28
R2R | 5 | CHS4_C_875 | FI - G/L account | Master Data | 1.1 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-01 | 2025-07-02
R2R | 6 | CHS4_C_875 | FI - G/L account | Master Data | 1.1 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-02 | 2025-07-03
R2R | 7 | CHS4_MAN04 | PC Hierarchy - Manual | Master Data | 1.2 | CHS4_C_893 | Main task
R2R | 8 | CHS4_MAN04 | PC Hierarchy - Manual | Master Data | 1.2 |  | Load Data File | Manual | R2R | TBD |  | 2025-07-01 | 2025-07-02
R2R | 9 | CHS4_MAN04 | PC Hierarchy - Manual | Master Data | 1.2 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-02 | 2025-07-03
R2R | 10 | CHS4_MAN03 | Cost Center Hierarchy - Manual | Master Data | 1.3 |  | Main task
R2R | 11 | CHS4_MAN03 | Cost Center Hierarchy - Manual | Master Data | 1.3 |  | Load Data File | Manual | R2R | TBD |  | 2025-07-01 | 2025-07-02
R2R | 12 | CHS4_MAN03 | Cost Center Hierarchy - Manual | Master Data | 1.3 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-02 | 2025-07-03
R2R | 13 | CHS4_C_871 | CO - Profit center | Master Data | 1.4 | CHS4_MAN04 | Main task
R2R | 14 | CHS4_C_871 | CO - Profit center | Master Data | 1.4 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-06-25 | 2025-06-26
R2R | 15 | CHS4_C_871 | CO - Profit center | Master Data | 1.4 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-06-26 | 2025-06-27
R2R | 16 | CHS4_C_871 | CO - Profit center | Master Data | 1.4 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-06-27 | 2025-06-28
R2R | 17 | CHS4_C_871 | CO - Profit center | Master Data | 1.4 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-02 | 2025-07-03
R2R | 18 | CHS4_C_871 | CO - Profit center | Master Data | 1.4 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-03 | 2025-07-04
R2R | 19 | CHS4_C_872 | CO - Cost center | Master Data | 1.5 | CHS4_MAN03,CHS4_C_871 | Main task
R2R | 20 | CHS4_C_872 | CO - Cost center | Master Data | 1.5 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-06-25 | 2025-06-26
R2R | 21 | CHS4_C_872 | CO - Cost center | Master Data | 1.5 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-06-26 | 2025-06-27
R2R | 22 | CHS4_C_872 | CO - Cost center | Master Data | 1.5 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-06-27 | 2025-06-28
R2R | 23 | CHS4_C_872 | CO - Cost center | Master Data | 1.5 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-02 | 2025-07-03
R2R | 24 | CHS4_C_872 | CO - Cost center | Master Data | 1.5 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-03 | 2025-07-04
R2R | 25 | CHS4_C_870 | Bank Master | Master Data | 1.6 |  | Main task
R2R | 26 | CHS4_C_870 | Bank Master | Master Data | 1.6 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-06-25 | 2025-06-26
R2R | 27 | CHS4_C_870 | Bank Master | Master Data | 1.6 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-06-26 | 2025-06-27
R2R | 28 | CHS4_C_870 | Bank Master | Master Data | 1.6 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-06-27 | 2025-06-28
R2R | 29 | CHS4_C_870 | Bank Master | Master Data | 1.6 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-03 | 2025-07-04
R2R | 30 | CHS4_C_870 | Bank Master | Master Data | 1.6 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-04 | 2025-07-05
MD | 31 | CHS4_C_883 | Site Characteristic | Master Data | 2.1 | CHS4_C_884 | Main task
MD | 32 | CHS4_C_883 | Site Characteristic | Master Data | 2.1 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-01 | 2025-07-02
MD | 33 | CHS4_C_883 | Site Characteristic | Master Data | 2.1 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-02 | 2025-07-03
MD | 34 | CHS4_C_883 | Site Characteristic | Master Data | 2.1 |  | Simulate Data File |  | Data Migration (DM) | Sona |  | 2025-07-03 | 2025-07-04
MD | 35 | CHS4_C_883 | Site Characteristic | Master Data | 2.1 |  | Load Data File | DMC | Data Migration (DM) | Sona |  | 2025-07-07 | 2025-07-08
MD | 36 | CHS4_C_883 | Site Characteristic | Master Data | 2.1 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-08 | 2025-07-09
MD | 37 | CHS4_C_884 | Site Class | Master Data | 2.1 |  | Main task
MD | 38 | CHS4_C_884 | Site Class | Master Data | 2.1 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-01 | 2025-07-02
MD | 39 | CHS4_C_884 | Site Class | Master Data | 2.1 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-02 | 2025-07-03
MD | 40 | CHS4_C_884 | Site Class | Master Data | 2.1 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-03 | 2025-07-04
MD | 41 | CHS4_C_884 | Site Class | Master Data | 2.1 |  | Load Data File | Manual | Data Migration (DM) | Manoj |  | 2025-07-07 | 2025-07-08
MD | 42 | CHS4_C_884 | Site Class | Master Data | 2.1 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-08 | 2025-07-09
RET | 43 | CHS4_C_867 | Convert Vision Sites to S4 BP | Master Data | 2.2 | CHS4_C_871 | Main task
RET | 44 | CHS4_C_867 | Convert Vision Sites to S4 BP | Master Data | 2.2 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-02 | 2025-07-03
RET | 45 | CHS4_C_867 | Convert Vision Sites to S4 BP | Master Data | 2.2 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-03 | 2025-07-04
RET | 46 | CHS4_C_867 | Convert Vision Sites to S4 BP | Master Data | 2.2 |  | Simulate Data File |  | Data Migration (DM) | Sona |  | 2025-07-04 | 2025-07-05
RET | 47 | CHS4_C_867 | Convert Vision Sites to S4 BP | Master Data | 2.2 |  | Load Data File | DMC | Data Migration (DM) | Sona |  | 2025-07-08 | 2025-07-09
RET | 48 | CHS4_C_867 | Convert Vision Sites to S4 BP | Master Data | 2.2 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-09 | 2025-07-10
MD | 49 | CHS4_C_882 | Sites and DCs | Master Data | 2.2 | CHS4_MAN04 | Main task
MD | 50 | CHS4_C_882 | Sites and DCs | Master Data | 2.2 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-02 | 2025-07-03
MD | 51 | CHS4_C_882 | Sites and DCs | Master Data | 2.2 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-03 | 2025-07-04
MD | 52 | CHS4_C_882 | Sites and DCs | Master Data | 2.2 |  | Simulate Data File |  | Data Migration (DM) | Sona |  | 2025-07-04 | 2025-07-05
MD | 53 | CHS4_C_882 | Sites and DCs | Master Data | 2.2 |  | Load Data File | LSMW | Data Migration (DM) | Sona |  | 2025-07-08 | 2025-07-09
MD | 54 | CHS4_C_882 | Sites and DCs | Master Data | 2.2 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-09 | 2025-07-10
MD | 55 | CHS4_C_927 | Site Classification | Master Data | 2.3 | CHS4_C_882, CHS4_C_883, CHS4_C_884 | Main task
MD | 56 | CHS4_C_927 | Site Classification | Master Data | 2.3 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-03 | 2025-07-04
MD | 57 | CHS4_C_927 | Site Classification | Master Data | 2.3 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-04 | 2025-07-05
MD | 58 | CHS4_C_927 | Site Classification | Master Data | 2.3 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-05 | 2025-07-06
MD | 59 | CHS4_C_927 | Site Classification | Master Data | 2.3 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-09 | 2025-07-10
MD | 60 | CHS4_C_927 | Site Classification | Master Data | 2.3 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-10 | 2025-07-11
R2R | 61 | CHS4_MAN01 | Exchange Rates - Manual | Master Data | 2.4 |  | Main task
R2R | 62 | CHS4_MAN02 | Exchange Rates - Manual | Master Data | 2.4 |  | Load Data File | Manual | R2R | TBD |  | 2025-07-11 | 2025-07-12
R2R | 63 | CHS4_MAN03 | Exchange Rates - Manual | Master Data | 2.4 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-12 | 2025-07-13
RET | 64 | CHS4_C_893 | Customer (All Views and contact persons) | Master Data | 2.5 | CHS4_C_875, CHS4_C_870 | Main task
RET | 65 | CHS4_C_893 | Customer (All Views and contact persons) | Master Data | 2.5 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-03 | 2025-07-04
RET | 66 | CHS4_C_893 | Customer (All Views and contact persons) | Master Data | 2.5 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-04 | 2025-07-05
RET | 67 | CHS4_C_893 | Customer (All Views and contact persons) | Master Data | 2.5 |  | Simulate Data File |  | Data Migration (DM) | Anu |  | 2025-07-05 | 2025-07-06
RET | 68 | CHS4_C_893 | Customer (All Views and contact persons) | Master Data | 2.5 |  | Load Data File | DMC | Data Migration (DM) | Anu |  | 2025-07-10 | 2025-07-11
RET | 69 | CHS4_C_893 | Customer (All Views and contact persons) | Master Data | 2.5 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-11 | 2025-07-12
RET | 70 | CHS4_C_899 | Supplier(All Views) | Master Data | 2.6 | CHS4_C_875, CHS4_C_870 | Main task
RET | 71 | CHS4_C_899 | Supplier(All Views) | Master Data | 2.6 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-03 | 2025-07-04
RET | 72 | CHS4_C_899 | Supplier(All Views) | Master Data | 2.6 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-04 | 2025-07-05
RET | 73 | CHS4_C_899 | Supplier(All Views) | Master Data | 2.6 |  | Simulate Data File |  | Data Migration (DM) | Sharon |  | 2025-07-05 | 2025-07-06
RET | 74 | CHS4_C_899 | Supplier(All Views) | Master Data | 2.6 |  | Load Data File | DMC | Data Migration (DM) | Sharon |  | 2025-07-10 | 2025-07-11
RET | 75 | CHS4_C_899 | Supplier(All Views) | Master Data | 2.6 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-11 | 2025-07-12
R2R | 76 | CHS4_C_881 | Customer - extend existing record by credit management data | Master Data | 2.7 |  | Main task
R2R | 77 | CHS4_C_881 | Customer - extend existing record by credit management data | Master Data | 2.7 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-08 | 2025-07-09
R2R | 78 | CHS4_C_881 | Customer - extend existing record by credit management data | Master Data | 2.7 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-09 | 2025-07-10
R2R | 79 | CHS4_C_881 | Customer - extend existing record by credit management data | Master Data | 2.7 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-10 | 2025-07-11
R2R | 80 | CHS4_C_881 | Customer - extend existing record by credit management data | Master Data | 2.7 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-14 | 2025-07-15
R2R | 81 | CHS4_C_881 | Customer - extend existing record by credit management data | Master Data | 2.7 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-15 | 2025-07-16
R2R | 82 | CHS4_C_880 | CO - Internal order | Master Data | 2.8 | CHS4_C_872 | Main task
R2R | 83 | CHS4_C_880 | CO - Internal order | Master Data | 2.8 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-08 | 2025-07-09
R2R | 84 | CHS4_C_880 | CO - Internal order | Master Data | 2.8 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-09 | 2025-07-10
R2R | 85 | CHS4_C_880 | CO - Internal order | Master Data | 2.8 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-10 | 2025-07-11
R2R | 86 | CHS4_C_880 | CO - Internal order | Master Data | 2.8 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-14 | 2025-07-15
R2R | 87 | CHS4_C_880 | CO - Internal order | Master Data | 2.8 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-15 | 2025-07-16
R2R | 88 | CHS4_MAN02 | ALL - TVARVC entries | Master Data | 3.1 |  | Main task
R2R | 89 | CHS4_MAN02 | ALL - TVARVC entries | Master Data | 3.1 |  | Load Data File | Manual | R2R | TBD |  | 2025-07-11 | 2025-07-12
R2R | 90 | CHS4_MAN02 | ALL - TVARVC entries | Master Data | 3.1 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-12 | 2025-07-13
RET | 91 | CHS4_C_864 | Convert AFS ECC BP to S4 BP | Master Data | 3.2 | CHS4_C_882 | Main task
RET | 92 | CHS4_C_864 | Convert AFS ECC BP to S4 BP | Master Data | 3.2 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-07 | 2025-07-08
RET | 93 | CHS4_C_864 | Convert AFS ECC BP to S4 BP | Master Data | 3.2 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-08 | 2025-07-09
RET | 94 | CHS4_C_864 | Convert AFS ECC BP to S4 BP | Master Data | 3.2 |  | Simulate Data File |  | Data Migration (DM) | Sona |  | 2025-07-09 | 2025-07-10
RET | 95 | CHS4_C_864 | Convert AFS ECC BP to S4 BP | Master Data | 3.2 |  | Load Data File | DMC | Data Migration (DM) | Sona |  | 2025-07-11 | 2025-07-12
RET | 96 | CHS4_C_864 | Convert AFS ECC BP to S4 BP | Master Data | 3.2 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-12 | 2025-07-13
P2P | 97 | CHS4_MAN05 | Fabric content | Master Data | 3.3 |  | Main task
P2P | 98 | CHS4_MAN05 | Fabric content | Master Data | 3.3 |  | Load Data File | Manual | P2P | TBD |  | 2025-07-15 | 2025-07-16
P2P | 99 | CHS4_MAN05 | Fabric content | Master Data | 3.3 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
P2P | 100 | CHS4_MAN06 | Franchise | Master Data | 3.4 |  | Main task
P2P | 101 | CHS4_MAN06 | Franchise | Master Data | 3.4 |  | Load Data File | Manual | P2P | TBD |  | 2025-07-15 | 2025-07-16
P2P | 102 | CHS4_MAN06 | Franchise | Master Data | 3.4 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
MD | 103 | CHS4_LSMW12 | Season Master creation | Master Data | 3.5 |  | Main task
MD | 104 | CHS4_LSMW12 | Season Master creation | Master Data | 3.5 |  | Load Data File | LSMW | MD | TBD |  | 2025-07-15 | 2025-07-16
MD | 105 | CHS4_LSMW12 | Season Master creation | Master Data | 3.5 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
MD | 106 | CHS4_LSMW08 | Season date upload | Master Data | 3.6 | CHS4_LSMW08 | Main task
MD | 107 | CHS4_LSMW08 | Season date upload | Master Data | 3.6 |  | Load Data File | LSMW | MD | TBD |  | 2025-07-15 | 2025-07-16
MD | 108 | CHS4_LSMW08 | Season date upload | Master Data | 3.6 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
MD | 109 | CHS4_LSMW09 | Add Season BU (MARC-ZZLABOR) update to this list | Master Data | 3.7 | CHS4_C_887, CHS4_C_882 | Main task
MD | 110 | CHS4_LSMW09 | Add Season BU (MARC-ZZLABOR) update to this list | Master Data | 3.7 |  | Load Data File | LSMW | MD | TBD |  | 2025-07-16 | 2025-07-17
MD | 111 | CHS4_LSMW09 | Add Season BU (MARC-ZZLABOR) update to this list | Master Data | 3.7 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-17 | 2025-07-18
R2R | 112 | CHS4_C_873 | FI - Accounts payable open item | Transaction Data | 4.1 | CHS4_C_871, CHS4_C_875, CHS4_C_899 | Main task
R2R | 113 | CHS4_C_873 | FI - Accounts payable open item | Transaction Data | 4.1 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-15 | 2025-07-16
R2R | 114 | CHS4_C_873 | FI - Accounts payable open item | Transaction Data | 4.1 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
R2R | 115 | CHS4_C_873 | FI - Accounts payable open item | Transaction Data | 4.1 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-17 | 2025-07-18
R2R | 116 | CHS4_C_873 | FI - Accounts payable open item | Transaction Data | 4.1 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-21 | 2025-07-22
R2R | 117 | CHS4_C_873 | FI - Accounts payable open item | Transaction Data | 4.1 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-22 | 2025-07-23
R2R | 118 | CHS4_C_874 | FI - Accounts receivable open item | Transaction Data | 4.2 | CHS4_C_871, CHS4_C_875, CHS4_C_893 | Main task
R2R | 119 | CHS4_C_874 | FI - Accounts receivable open item | Transaction Data | 4.2 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-15 | 2025-07-16
R2R | 120 | CHS4_C_874 | FI - Accounts receivable open item | Transaction Data | 4.2 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
R2R | 121 | CHS4_C_874 | FI - Accounts receivable open item | Transaction Data | 4.2 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-17 | 2025-07-18
R2R | 122 | CHS4_C_874 | FI - Accounts receivable open item | Transaction Data | 4.2 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-21 | 2025-07-22
R2R | 123 | CHS4_C_874 | FI - Accounts receivable open item | Transaction Data | 4.2 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-22 | 2025-07-23
R2R | 124 | CHS4_C_876 | FI - G/L account balance and open/line item | Transaction Data | 4.3 | CHS4_C_871, CHS4_C_875, CHS4_C_872 | Main task
R2R | 125 | CHS4_C_876 | FI - G/L account balance and open/line item | Transaction Data | 4.3 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-16 | 2025-07-17
R2R | 126 | CHS4_C_876 | FI - G/L account balance and open/line item | Transaction Data | 4.3 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-17 | 2025-07-18
R2R | 127 | CHS4_C_876 | FI - G/L account balance and open/line item | Transaction Data | 4.3 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-18 | 2025-07-19
R2R | 128 | CHS4_C_876 | FI - G/L account balance and open/line item | Transaction Data | 4.3 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-22 | 2025-07-23
R2R | 129 | CHS4_C_876 | FI - G/L account balance and open/line item | Transaction Data | 4.3 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-23 | 2025-07-24
R2R | 130 | CHS4_C_879 | Fixed asset - Master data | Master Data | 4.4 | CHS4_C_871, CHS4_C_872 | Main task
R2R | 131 | CHS4_C_879 | Fixed asset - Master data | Master Data | 4.4 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-24 | 2025-07-25
R2R | 132 | CHS4_C_879 | Fixed asset - Master data | Master Data | 4.4 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-25 | 2025-07-26
R2R | 133 | CHS4_C_879 | Fixed asset - Master data | Master Data | 4.4 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-26 | 2025-07-27
R2R | 134 | CHS4_C_879 | Fixed asset - Master data | Master Data | 4.4 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-28 | 2025-07-29
R2R | 135 | CHS4_C_879 | Fixed asset - Master data | Master Data | 4.4 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-29 | 2025-07-30
R2R | 136 | CHS4_C_878 | Fixed asset (incl. balances and transactions) | Transaction Data | 4.5 | CHS4_C_871, CHS4_C_875 | Main task
R2R | 137 | CHS4_C_878 | Fixed asset (incl. balances and transactions) | Transaction Data | 4.5 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-24 | 2025-07-25
R2R | 138 | CHS4_C_878 | Fixed asset (incl. balances and transactions) | Transaction Data | 4.5 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-25 | 2025-07-26
R2R | 139 | CHS4_C_878 | Fixed asset (incl. balances and transactions) | Transaction Data | 4.5 |  | Simulate Data File |  | Data Migration (DM) | Manoj |  | 2025-07-26 | 2025-07-27
R2R | 140 | CHS4_C_878 | Fixed asset (incl. balances and transactions) | Transaction Data | 4.5 |  | Load Data File | DMC | Data Migration (DM) | Manoj |  | 2025-07-28 | 2025-07-29
R2R | 141 | CHS4_C_878 | Fixed asset (incl. balances and transactions) | Transaction Data | 4.5 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-29 | 2025-07-30
RET | 142 | CHS4_LSMW05 | Assortment Creation | Master Data | 4.6 | CHS4_C_882, CHS4_C_886 | Main task
RET | 143 | CHS4_LSMW05 | Assortment Creation | Master Data | 4.6 |  | Load Data File | LSMW | RET | TBD |  | 2025-07-21 | 2025-07-22
RET | 144 | CHS4_LSMW05 | Assortment Creation | Master Data | 4.6 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-22 | 2025-07-23
MD | 145 | CHS4_C_886 | Material Group | Master Data | 5.1 |  | Main task
MD | 146 | CHS4_C_886 | Material Group | Master Data | 5.1 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-03 | 2025-07-04
MD | 147 | CHS4_C_886 | Material Group | Master Data | 5.1 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-04 | 2025-07-05
MD | 148 | CHS4_C_886 | Material Group | Master Data | 5.1 |  | Simulate Data File |  | Data Migration (DM) | Sona |  | 2025-07-05 | 2025-07-06
MD | 149 | CHS4_C_886 | Material Group | Master Data | 5.1 |  | Load Data File | DMC | Data Migration (DM) | Sona |  | 2025-07-11 | 2025-07-12
MD | 150 | CHS4_C_886 | Material Group | Master Data | 5.1 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-12 | 2025-07-13
RET | 151 | CHS4_C_895 | Customer - extend existing record by new org levels | Master Data | 5.2 | CHS4_C_893 | Main task
RET | 152 | CHS4_C_895 | Customer - extend existing record by new org levels | Master Data | 5.2 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-04 | 2025-07-05
RET | 153 | CHS4_C_895 | Customer - extend existing record by new org levels | Master Data | 5.2 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-05 | 2025-07-06
RET | 154 | CHS4_C_895 | Customer - extend existing record by new org levels | Master Data | 5.2 |  | Simulate Data File |  | Data Migration (DM) | Anu |  | 2025-07-06 | 2025-07-07
RET | 155 | CHS4_C_895 | Customer - extend existing record by new org levels | Master Data | 5.2 |  | Load Data File | DMC | Data Migration (DM) | Anu |  | 2025-07-10 | 2025-07-11
RET | 156 | CHS4_C_895 | Customer - extend existing record by new org levels | Master Data | 5.2 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-11 | 2025-07-12
RET | 157 | CHS4_C_901 | Supplier - extend existing record by new org levels | Master Data | 5.3 | CHS4_C_899 | Main task
RET | 158 | CHS4_C_901 | Supplier - extend existing record by new org levels | Master Data | 5.3 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-04 | 2025-07-05
RET | 159 | CHS4_C_901 | Supplier - extend existing record by new org levels | Master Data | 5.3 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-05 | 2025-07-06
RET | 160 | CHS4_C_901 | Supplier - extend existing record by new org levels | Master Data | 5.3 |  | Simulate Data File |  | Data Migration (DM) | Sharon |  | 2025-07-06 | 2025-07-07
RET | 161 | CHS4_C_901 | Supplier - extend existing record by new org levels | Master Data | 5.3 |  | Load Data File | DMC | Data Migration (DM) | Sharon |  | 2025-07-10 | 2025-07-11
RET | 162 | CHS4_C_901 | Supplier - extend existing record by new org levels | Master Data | 5.3 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-11 | 2025-07-12
P2P | 163 | CHS4_C_887 | Material Master (CHS4_C_887) | Master Data | 5.5 | CHS4_C_871, CHS4_C_882 | Main task
P2P | 164 | CHS4_C_887 | Material Master (CHS4_C_887) | Master Data | 5.5 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-08 | 2025-07-09
P2P | 165 | CHS4_C_887 | Material Master (CHS4_C_887) | Master Data | 5.5 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-09 | 2025-07-10
P2P | 166 | CHS4_C_887 | Material Master (CHS4_C_887) | Master Data | 5.5 |  | Load Data File | Interface | Integration (BOOMI) | TBD |  | 2025-07-14 | 2025-07-15
P2P | 167 | CHS4_C_887 | Material Master (CHS4_C_887) | Master Data | 5.5 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-15 | 2025-07-16
P2P | 168 | CHS4_C_888 | Material Master - extend existing record by new org levels (CHS4_C_888) | Master Data | 5.6 | CHS4_C_887 | Main task
P2P | 169 | CHS4_C_888 | Material Master - extend existing record by new org levels (CHS4_C_888) | Master Data | 5.6 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-10 | 2025-07-11
P2P | 170 | CHS4_C_888 | Material Master - extend existing record by new org levels (CHS4_C_888) | Master Data | 5.6 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-11 | 2025-07-12
P2P | 171 | CHS4_C_888 | Material Master - extend existing record by new org levels (CHS4_C_888) | Master Data | 5.6 |  | Load Data File | Interface | Integration (BOOMI) | TBD |  | 2025-07-16 | 2025-07-17
P2P | 172 | CHS4_C_888 | Material Master - extend existing record by new org levels (CHS4_C_888) | Master Data | 5.6 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-17 | 2025-07-18
O2C | 173 | CHS4_C_896 | Material listing CHS4_C_896 | Master Data | 5.7 | CH_S4_C_887, CHS4_LSMW04 | Main task
O2C | 174 | CHS4_C_896 | Material listing CHS4_C_896 | Master Data | 5.7 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-12 | 2025-07-13
O2C | 175 | CHS4_C_896 | Material listing CHS4_C_896 | Master Data | 5.7 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-13 | 2025-07-14
O2C | 176 | CHS4_C_896 | Material listing CHS4_C_896 | Master Data | 5.7 |  | Load Data File | Interface | Integration (BOOMI) | TBD |  | 2025-07-18 | 2025-07-19
O2C | 177 | CHS4_C_896 | Material listing CHS4_C_896 | Master Data | 5.7 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-19 | 2025-07-20
P2P | 178 | CHS4_C_902 | MM - Purchasing info record with conditions | Master Data | 5.8 | CHS4_C_882, CHS4_C_887, | Main task
P2P | 179 | CHS4_C_902 | MM - Purchasing info record with conditions | Master Data | 5.8 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-15 | 2025-07-16
P2P | 180 | CHS4_C_902 | MM - Purchasing info record with conditions | Master Data | 5.8 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
P2P | 181 | CHS4_C_902 | MM - Purchasing info record with conditions | Master Data | 5.8 |  | Load Data File | Interface | Integration (BOOMI) | TBD |  | 2025-07-21 | 2025-07-22
P2P | 182 | CHS4_C_902 | MM - Purchasing info record with conditions | Master Data | 5.8 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-22 | 2025-07-23
P2P | 183 | CHS4_C_903 | Condition record for pricing in purchasing (restricted) | Master Data | 5.9 | CHS4_C_887, CHS4_C_903 | Main task
P2P | 184 | CHS4_C_903 | Condition record for pricing in purchasing (restricted) | Master Data | 5.9 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-15 | 2025-07-16
P2P | 185 | CHS4_C_903 | Condition record for pricing in purchasing (restricted) | Master Data | 5.9 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
P2P | 186 | CHS4_C_903 | Condition record for pricing in purchasing (restricted) | Master Data | 5.9 |  | Load Data File | Interface | Integration (BOOMI) | TBD |  | 2025-07-21 | 2025-07-22
P2P | 187 | CHS4_C_903 | Condition record for pricing in purchasing (restricted) | Master Data | 5.9 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-22 | 2025-07-23
P2P | 188 | CHS4_C_909 | MM - Source list | Master Data | 5.10 | CHS4_C_882, CHS4_C_887, | Main task
P2P | 189 | CHS4_C_909 | MM - Source list | Master Data | 5.10 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-15 | 2025-07-16
P2P | 190 | CHS4_C_909 | MM - Source list | Master Data | 5.10 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
P2P | 191 | CHS4_C_909 | MM - Source list | Master Data | 5.10 |  | Load Data File | Interface | Integration (BOOMI) | TBD |  | 2025-07-22 | 2025-07-23
P2P | 192 | CHS4_C_909 | MM - Source list | Master Data | 5.10 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-23 | 2025-07-24
P2P | 193 | CHS4_LSMW01 | Program to update UPC number for materials | Master Data | 5.11 | CHS4_C_887 | Main task
P2P | 194 | CHS4_LSMW01 | Program to update UPC number for materials | Master Data | 5.11 |  | Load Data File | LSMW | P2P | TBD |  | 2025-07-22 | 2025-07-23
P2P | 195 | CHS4_LSMW01 | Program to update UPC number for materials | Master Data | 5.11 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-23 | 2025-07-24
P2P | 196 | CHS4_LSMW10 | PIR for material group (manual) | Master Data | 5.12 | CHS4_C_899 | Main task
P2P | 197 | CHS4_LSMW10 | PIR for material group (manual) | Master Data | 5.12 |  | Load Data File | LSMW | P2P | TBD |  | 2025-07-22 | 2025-07-23
P2P | 198 | CHS4_LSMW10 | PIR for material group (manual) | Master Data | 5.12 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-23 | 2025-07-24
P2P | 199 | CHS4_LSMW11 | 37 ZAWA materials,2 NLAG materials, 1 VERP (manual) | Master Data | 5.13 | CHS4_C_882, CHS4_C_871, CHS4_C_899 | Main task
P2P | 200 | CHS4_LSMW11 | 37 ZAWA materials,2 NLAG materials, 1 VERP (manual) | Master Data | 5.13 |  | Load Data File | LSMW | P2P | TBD |  | 2025-07-15 | 2025-07-16
P2P | 201 | CHS4_LSMW11 | 37 ZAWA materials,2 NLAG materials, 1 VERP (manual) | Master Data | 5.13 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-16 | 2025-07-17
P2P | 202 | CHS4_LSMW13 | UPC upload for Non-licensing product | Master Data | 5.14 | CHS4_C_887 | Main task
P2P | 203 | CHS4_LSMW13 | UPC upload for Non-licensing product | Master Data | 5.14 |  | Load Data File | LSMW | P2P | TBD |  | 2025-07-22 | 2025-07-23
P2P | 204 | CHS4_LSMW13 | UPC upload for Non-licensing product | Master Data | 5.14 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-23 | 2025-07-24
MD | 205 | CHS4_LSMW07 | Commodity code upload | Master Data | 5.15 |  | Main task
MD | 206 | CHS4_LSMW07 | Commodity code upload | Master Data | 5.15 |  | Load Data File | LSMW | MD | TBD |  | 2025-07-16 | 2025-07-17
MD | 207 | CHS4_LSMW07 | Commodity code upload | Master Data | 5.15 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-17 | 2025-07-18
P2P | 208 | CHS4_C_905 | Material inventory balance (AFS) | Transaction Data | 6.1 | CHS4_C_887, CHS4_C_882, CHS4_C_875 | Main task
P2P | 209 | CHS4_C_905 | Material inventory balance (AFS) | Transaction Data | 6.1 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-23 | 2025-07-24
P2P | 210 | CHS4_C_905 | Material inventory balance (AFS) | Transaction Data | 6.1 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-24 | 2025-07-25
P2P | 211 | CHS4_C_905 | Material inventory balance (AFS) | Transaction Data | 6.1 |  | Simulate Data File |  |  | Sharon |  | 2025-07-25 | 2025-07-26
P2P | 212 | CHS4_C_905 | Material inventory balance (AFS) | Transaction Data | 6.1 |  | Load Data File | DMC | Data Migration (DM) | Sharon |  | 2025-07-29 | 2025-07-30
P2P | 213 | CHS4_C_905 | Material inventory balance (AFS) | Transaction Data | 6.1 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-30 | 2025-07-31
P2P | 214 | CHS4_C_907 | MM - Purchase order (only open PO) (AFS) | Transaction Data | 6.2 | CHS4_C_882, CHS4_C_887,CHS4_C_899 | Main task
P2P | 215 | CHS4_C_907 | MM - Purchase order (only open PO) (AFS) | Transaction Data | 6.2 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-18 | 2025-07-19
P2P | 216 | CHS4_C_907 | MM - Purchase order (only open PO) (AFS) | Transaction Data | 6.2 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-19 | 2025-07-20
P2P | 217 | CHS4_C_907 | MM - Purchase order (only open PO) (AFS) | Transaction Data | 6.2 |  | Simulate Data File |  |  | Sharon |  | 2025-07-20 | 2025-07-21
P2P | 218 | CHS4_C_907 | MM - Purchase order (only open PO) (AFS) | Transaction Data | 6.2 |  | Load Data File | DMC | Data Migration (DM) | Sharon |  | 2025-07-25 | 2025-07-26
P2P | 219 | CHS4_C_907 | MM - Purchase order (only open PO) (AFS) | Transaction Data | 6.2 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-26 | 2025-07-27
O2C | 220 | CHS4_C_891 | Condition record for pricing (general template) | Master Data | 6.3 | CHS4_C_887, CHS4_C_899 | Main task
O2C | 221 | CHS4_C_891 | Condition record for pricing (general template) | Master Data | 6.3 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-17 | 2025-07-18
O2C | 222 | CHS4_C_891 | Condition record for pricing (general template) | Master Data | 6.3 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-18 | 2025-07-19
O2C | 223 | CHS4_C_891 | Condition record for pricing (general template) | Master Data | 6.3 |  | Simulate Data File |  |  | Anu |  | 2025-07-19 | 2025-07-20
O2C | 224 | CHS4_C_891 | Condition record for pricing (general template) | Master Data | 6.3 |  | Load Data File | DMC | Data Migration (DM) | Anu |  | 2025-07-23 | 2025-07-24
O2C | 225 | CHS4_C_891 | Condition record for pricing (general template) | Master Data | 6.3 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-24 | 2025-07-25
O2C | 226 | CHS4_C_892 | Condition record for pricing in sales (restricted) | Master Data | 6.4 | CHS4_C_887, CHS4_C_893 | Main task
O2C | 227 | CHS4_C_892 | Condition record for pricing in sales (restricted) | Master Data | 6.4 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-17 | 2025-07-18
O2C | 228 | CHS4_C_892 | Condition record for pricing in sales (restricted) | Master Data | 6.4 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-18 | 2025-07-19
O2C | 229 | CHS4_C_892 | Condition record for pricing in sales (restricted) | Master Data | 6.4 |  | Simulate Data File |  |  | Anu |  | 2025-07-19 | 2025-07-20
O2C | 230 | CHS4_C_892 | Condition record for pricing in sales (restricted) | Master Data | 6.4 |  | Load Data File | DMC | Data Migration (DM) | Anu |  | 2025-07-23 | 2025-07-24
O2C | 231 | CHS4_C_892 | Condition record for pricing in sales (restricted) | Master Data | 6.4 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-24 | 2025-07-25
RET | 232 | CHS4_LSMW02 | Retail Pricing upload from Vision | Master Data | 6.5 | CHS4_C_887, CHS4_C_882 | Main task
RET | 233 | CHS4_LSMW02 | Retail Pricing upload from Vision | Master Data | 6.5 |  | Load Data File | LSMW | RET | TBD |  | 2025-07-23 | 2025-07-24
RET | 234 | CHS4_LSMW02 | Retail Pricing upload from Vision | Master Data | 6.5 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-24 | 2025-07-25
P2P | 235 | CHS4_LSMW03 | Store Inventory upload from Vision | Master Data | 6.6 | CHS4_MAN04, CHS4_C_875 | Main task
P2P | 236 | CHS4_LSMW03 | Store Inventory upload from Vision | Master Data | 6.6 |  | Load Data File | LSMW | P2P | TBD |  | 2025-07-29 | 2025-07-30
P2P | 237 | CHS4_LSMW03 | Store Inventory upload from Vision | Master Data | 6.6 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-30 | 2025-07-31
O2C | 238 | TBD | VAS Records | Master Data | 6.7 | CHS4_C_882, CHS4_C_887, | Main task
O2C | 239 | TBD | Output Conditions Records | Master Data | 6.8 | CHS4_C_882, CHS4_C_887, | Main task
P2P | 240 | TBD | Output Conditions Records | Master Data | 6.9 | CHS4_C_882, CHS4_C_887, | Main task
O2C | 241 | CHS4_C_897 | SD - Sales contract | Transaction Data | 6.10 | CHS4_C_887, CHS4_C_882 | Main task
O2C | 242 | CHS4_C_897 | SD - Sales contract | Transaction Data | 6.10 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-19 | 2025-07-20
O2C | 243 | CHS4_C_897 | SD - Sales contract | Transaction Data | 6.10 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-20 | 2025-07-21
O2C | 244 | CHS4_C_897 | SD - Sales contract | Transaction Data | 6.10 |  | Simulate Data File |  |  | Anu |  | 2025-07-21 | 2025-07-22
O2C | 245 | CHS4_C_897 | SD - Sales contract | Transaction Data | 6.10 |  | Load Data File | DMC | Data Migration (DM) | Anu |  | 2025-07-25 | 2025-07-26
O2C | 246 | CHS4_C_897 | SD - Sales contract | Transaction Data | 6.10 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-26 | 2025-07-27
O2C | 247 | CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | Transaction Data | 6.11 | CHS4_C_882, CHS4_C_887, | Main task
O2C | 248 | CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | Transaction Data | 6.11 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-19 | 2025-07-20
O2C | 249 | CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | Transaction Data | 6.11 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-20 | 2025-07-21
O2C | 250 | CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | Transaction Data | 6.11 |  | Simulate Data File |  |  | Anu |  | 2025-07-21 | 2025-07-22
O2C | 251 | CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | Transaction Data | 6.11 |  | Load Data File | DMC | Data Migration (DM) | Anu |  | 2025-07-25 | 2025-07-26
O2C | 252 | CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | Transaction Data | 6.11 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-26 | 2025-07-27
P2P | 253 | CHS4_LSMW04 | MM - Purchase order (only open PO) ( Vision) | Transaction Data | 6.12 | CHS4_C_882, CHS4_C_887, | Main task
P2P | 254 | CHS4_LSMW04 | MM - Purchase order (only open PO) ( Vision) | Transaction Data | 6.12 |  | Extract/Prepare Data File |  | CH IT Team | TBD |  | 2025-07-19 | 2025-07-20
P2P | 255 | CHS4_LSMW04 | MM - Purchase order (only open PO) ( Vision) | Transaction Data | 6.12 |  | Validate and Approve Preload Data File |  | CH Business / Workstream | TBD |  | 2025-07-20 | 2025-07-21
P2P | 256 | CHS4_LSMW04 | MM - Purchase order (only open PO) ( Vision) | Transaction Data | 6.12 |  | Simulate Data File |  |  | TBD |  | 2025-07-21 | 2025-07-22
P2P | 257 | CHS4_LSMW04 | MM - Purchase order (only open PO) ( Vision) | Transaction Data | 6.12 |  | Load Data File | LSMW | P2P | TBD |  | 2025-07-25 | 2025-07-26
P2P | 258 | CHS4_LSMW04 | MM - Purchase order (only open PO) ( Vision) | Transaction Data | 6.12 |  | Validate and Approve Data in Target S4 system |  | CH Business / Workstream | TBD |  | 2025-07-26 | 2025-07-27
R2R | 259 | CHS4_MAN07 | ZINTINV1 | Master Data | 6.13 | CHS4_C_898 | Main task
Formulas:
Start Date/Time = VLOOKUP([RICEFW ID],'[1]Dev Tracker'!$B:$Y,11,0)
Start Date/Time = +[Start Date/Time, row above]+1
End Date/Time = +[Start Date/Time]+1

## Mock 1 Plan (hidden)
WorkStream | RICEFW ID | Object Name/Description | Object type | Dependacy | Sequence | Load Tool
R2R | CHS4_MAN02 | ALL - TVARVC entries | MD |  | 1 | 0
R2R | CHS4_C_870 | Bank Master | MD |  | 1 | Complete
MD | CHS4_C_865 | Convert AFS ECC Customer Master to S4 BP | MD |  | 2 | 0
MD | CHS4_C_866 | Convert AFS ECC Vendor Master to S4 BP | MD |  | 2 | 0
RET | CHS4_C_893 | Customer (All Views and contact persons) | MD |  | 1 | 0
RET | CHS4_C_899 | Supplier(All Views) | MD |  | 1 | 0
R2R | CHS4_C_881 | Customer - extend existing record by credit management data | MD |  | 1 | 0
RET | CHS4_C_895 | Customer - extend existing record by new org levels | MD |  | 2 | 0
RET | CHS4_C_901 | Supplier - extend existing record by new org levels | MD |  | 2 | 0
MD | CHS4_C_883 | Site Characteristic | MD |  | 1 | Complete
MD | CHS4_C_884 | Site Class | MD |  | 1 | Complete
MD | CHS4_C_927 | Site Classification | MD |  | 1 | 0
MD | CHS4_C_882 | Sites and DCs | MD |  | 1 | 0
RET | CHS4_C_867 | Convert Vision/AFS Sites to S4 BP (customer and vendor) | MD | CHS4_C_882 | 1 | 0
MD | CHS4_MAN05 | Fabric content | MD |  | 1 | Complete
MD | CHS4_MAN06 | Franchise | MD |  | 1 | Complete
MD | Custom Tables | ZMM_GRIDTYPES | MD |  | 1 | #N/A
MD | Custom Tables | ZMM_MATERIALGRID | MD |  | 1 | #N/A
MD | Custom Tables | ZMM_PURCHASEGRID | MD |  | 1 | #N/A
MD | Custom Tables | ZMM_SALESGRID | MD |  | 1 | #N/A
MD | Custom Tables | ZSIZECODES | MD |  | 1 | #N/A
MD | Manual | Variant Characteristics | MD |  | 1 | #N/A
MD | Manual | Variant Characteristics Values | MD |  | 1 | #N/A
MD | Manual | Variant Cofiguration Class | MD |  | 1 | #N/A
R2R | CHS4_MAN04 | PC Hierarchy - Manual | MD |  | 2 | N/A
R2R | CHS4_C_871 | CO - Profit center | MD | CHS4_MAN04 | 2 | Complete
R2R | CHS4_MAN03 | Cost Center Hierarchy - Manual | MD |  | 2 | N/A
R2R | CHS4_C_872 | CO - Cost center | MD | CHS4_MAN03/CHS4_C_871 | 2 | Complete
R2R | CHS4_C_875 | FI - G/L account | MD |  | 1 | Complete
R2R | CHS4_MAN01 | Exchange Rates - Manual | MD |  | 1 | 0
R2R | CHS4_C_880 | CO - Internal order | MD |  | 3 | Complete
MD | CHS4_C_886 | Material Group | MD |  | 3 | Complete
MD | CHS4_LSMW13 | UPC upload for Non-licensing product (ZPLM_UPC) | MD |  | 3 | 0
MD | Custom Tables | ZUPCXREF | MD |  | 3 | #N/A
MD | CHS4_LSMW07 | Commodity code upload | MD |  | 3 | Complete
MD | CHS4_LSMW06 | Season Master creation | MD |  | 3 | #N/A
MD | CHS4_LSMW08 | Season date upload | MD |  | 3 | Complete
MD | CHS4_C_887 | Material Master (CHS4_C_887) | MD |  | 3
MD | CHS4_C_888 | Material Master - extend existing record by new org levels (CHS4_C_888) and Listing | MD |  | 3
MD | CHS4_C_896 | Material listing and exclusionCHS4_C_896 | MD |  | 3
MD | CHS4_LSMW11 | 37 ZAWA materials,2 NLAG materials, 1 VERP (manual) | MD |  | 3 | 0
MD | CHS4_C_902 | MM - Purchasing info record with conditions(descope) | MD |  | 3 | N/A
MD | CHS4_LSMW10 | PIR for material group (manual) | MD |  | 3 | Complete
MD | CHS4_C_903 | Condition record for pricing in purchasing (restricted)(Descope) | MD |  | 3 | N/A
MD | CHS4_C_909 | MM - Source list(Descope) | MD |  | 3 | 0
MD | CHS4_LSMW01 | Program to update UPC number for materials | MD |  | 3 | Complete
MD | CHS4_LSMW09 | Add Season BU (MARC-ZZLABOR) update to this list | MD |  | 3 | Complete
RET | CHS4_LSMW05 | Assortment Creation | MD |  | 4 | 0
O2C | CHS4_C_891 | Condition record for pricing (general template) | MD |  | 4 | 0
O2C | CHS4_C_892 | Condition record for pricing in sales (restricted) | MD |  | 4 | 0
RET | CHS4_LSMW02 | Retail Pricing upload from Vision | MD |  | 4 | 0
R2R | CHS4_C_879 | Fixed asset - Master data | MD |  | 3 | 0
R2R | CHS4_C_926 | Good Will Impairment Analysis | MD |  | 3 | 0
R2R | CHS4_MAN07 | ZINTINV1 | MD |  |  | 0
R2R | CHS4_C_873 | FI - Accounts payable open item | TD |  | 4 | 0
R2R | CHS4_C_874 | FI - Accounts receivable open item | TD |  | 4 | 0
R2R | CHS4_C_876 | FI - G/L account balance and open/line item | TD |  | 4 | 0
R2R | CHS4_C_878 | Fixed asset (incl. balances and transactions) | TD |  | 4 | 0
O2C | CHS4_C_897 | SD - Sales contract (Active only) | TD |  | 10 | 0
O2C | CHS4_C_898 | SD - Sales order (only open SO) | TD |  | 10 | 0
P2P | CHS4_C_907 | MM - Purchase order (only open PO) (AFS) | TD |  | 10 | 0
P2P | CHS4_LSMW04 | MM - Purchase order (only open PO) ( Vision) | TD |  | 10 | 0
P2P | CHS4_C_905 | Material inventory balance (AFS)(Quantity Upload) | TD |  | 10 | 0
P2P | CHS4_LSMW03 | Store Inventory upload from Vision | TD |  | 10 | 0
O2C |  | Output Conditions Records | MD |  | 4 | #N/A
O2C |  | VAS Records | MD |  | 4 | #N/A
RET | CHS4_C_894 | Customer - extend existing record by multiple addresses | MD
RET | CHS4_C_900 | Supplier - extend existing record by multiple addresses | MD

## Sheet2 (hidden)
Not Started | Awaiting Load File | Completed | InScope
In Progress | Data Received | Not Started | Out of Scope
On Hold | Data Issue; Awaiting Correction File
Completed

## Client Strategy (hidden)
Mock 1
S4D | 300 | 300 Create Project
| 400 | Switch client using LTMOM | Development / Unit Testing
S4Q
| 400 | Move using Transprot package 'ZDM' | Mock 1 Cient | Can we refresh for Mock 3 loads ?
| 410 | Switch client using LTMOM | Mock 2 Client
| 400 | Switch client using LTMOM | Mock 3 Client | Refresh after SIT 1 ? (If SIT 1 exceeds schedule and reaches Nov end instead of Oct end then Mock 3 client prep will be at RISK
| 420 | Switch client using LTMOM | Mock 4 Client
S4P | 300 | Move using Transprot package 'ZDM' | Prod Cutover

## Daily_Task_List (hidden)
SI.No | Month | Date | Task Details | Assigned To | Requested By | ETA | Task Status | Comments
1 |  | 2025-04-23 | GL Load | Manoj | Harshit | 2025-04-23 | Completed
2 |  | 2025-04-24 | Share DMC templates to R2R Team,Upload all templates to SharePoint | Sona,Sharon | Milind | 2025-04-25 | Completed | applexus.sharepoint
3 |  | 2025-04-24 | Update weekly status Doc DM | Manoj | Sami
4 |  | 2025-04-24 | Connect with walter to finalize client startegy for mock loads | Sami | Sami | 2025-04-25 | Completed
5 |  | 2025-04-24 | Update strategy Doc as per change in scope | Sona | Sami | 2025-04-25 | Completed | Cole Haan DataMigration - Strategy & Approach Draft_v3_loadonlydoc_WIP.docx
6 |  | 2025-04-24 | Send email for stream leads explaining SOP DM team | Manoj | Sami | 2025-04-29 | Completed
7 |  | 2025-04-24 | Check LSMW can be used for BP(Create BP) | Sona | Sami | 2025-04-25 |  | Connect with Sami to discuss
8 |  | 2025-04-25 | Create Project in DMC w.r.t.'CH Conversion List' | Sharon,Sona,Manoj | Sami | 2025-04-28 | Completed | Projects created for 'DM_Primary_Resource_Sharon'
9 |  | 2025-04-25 | Check Tcode access for all objects | Sharon | Sami | 2025-04-28 | Completed | Tcode check done in DEV 300
10 |  | 2025-04-25 | Upload 'Naming convention' document to sharepoint (onboarding documents) | Sona | Sami | 2025-04-25 | Completed | Naming_Convention_Cole_Haan.docx
11 |  | 2025-04-25 | Check the number of sites in sandbox | Sona | Sami | 2025-04-25 | Completed | 12 Sites in sandBox
12 |  | 2025-04-28 | Get a Transport pacakage 'ZDM' created for DMC transports | Manoj | Sami | 2025-04-30 | Completed
13 |  | 2025-04-28 | Create DMC Projects for all the DM Objects identified as DMC load method so far. (This depends on Transport package being created) | Manoj/Sharon | Sami | 2025-04-30 | Completed | Manoj working on Projects not added to 'ZDM'
14 |  | 2025-04-28 | Review DM Strategy Approach Document with Sona | Sami/Sona | Sami | 2025-04-29 | In-Progress
15 |  | 2025-04-28 | Create Mapping sheet template for Workstram Leads. This template will then be replicated for all objects as needed. | Sami | Sami | 2025-04-28 |  | Since extraction and transformation are not in our scope.
16 |  | 2025-04-28 | Prepare Client Strategy slide for approval (Bilal ? KC/KK) ? | Manoj | Sami | 2025-04-28 | Completed | send for review
|  | 2025-05-05 | Update DM onboarding document(Include Project creation under package) | Sharon | Sami | 2025-05-08 | In-Progress
|  |  | Connect with Vishnu or Xiao for the test data. | Sona | Sami | 2025-05-08 | In-Progress | Vishnu and Xiao confirmed to provide data this week.

## Mock1_Tracker (hidden)
SNO | WorkStream | RICEFW ID | Object Name/Description | DM Scope | Load Seq# | Predecessor | Actual Load Date From | Actual Load Date To | Load File Status | DM Resource | Source | Mapping Issue | Simulation Success | Simulation Failed | Loaded | Failed SAP Load | % Loaded (Loaded/source) | Load Status | Details/Comments | Laod Method | Program Details | Load Time | Postload Time | Workstream Lead | Business Lead
1 | RET | CHS4_C_864 | Convert AFS ECC BP to S4 BP | InScope | 1 | 1 | 2025-07-01 |  | Data Received | Sona | 100 | 2 | 98 | 2 | 98 | 2 | 98% | Not Started |  | DMC | PRJ_MD_CHS4_C_864_BP_ECC_M05 |  |  | Vishnu/Xiao
2 | RET | CHS4_C_865 | Convert AFS ECC Customer Master to S4 BP | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | In Progress |  | DMC | PRJ_MD_CHS4_C_865_BP_Customer_M06 |  |  | Vishnu/Xiao
3 | RET | CHS4_C_866 | Convert AFS ECC Vendor Master to S4 BP | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | In Progress |  | DMC | PRJ_MD_CHS4_C_866_BP_supplier_M07 |  |  | Vishnu/Xiao
4 | RET | CHS4_C_867 | Convert Vision Sites to S4 BP | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | In Progress |  | DMC | PRJ_MD_CHS4_C_867_BP_VisionSites_M1F |  |  | Vishnu/Xiao
5 | R2R | CHS4_C_870 | Bank Master | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_870_Bank Master_M0R |  |  | Binoj/Harshit
6 | R2R | CHS4_C_871 | CO - Profit center | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_871_Profit center_M0S |  |  | Binoj/Harshit
7 | R2R | CHS4_C_872 | CO - Cost center | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_872_Cost center |  |  | Binoj/Harshit
8 | R2R | CHS4_C_873 | FI - Accounts payable open item | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_873_AP |  |  | Binoj/Harshit
9 | R2R | CHS4_C_874 | FI - Accounts receivable open item | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_874_AR |  |  | Binoj/Harshit
10 | R2R | CHS4_C_875 | FI - G/L account | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_875_GL_M0A |  |  | Binoj/Harshit
11 | R2R | CHS4_C_876 | FI - G/L account balance and open/line item | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_876_GL_Openitem_Balance_M0B |  |  | Binoj/Harshit
12 | R2R | CHS4_C_878 | Fixed asset (incl. balances and transactions) | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_878_Asset_TD_MOC |  |  | Binoj/Harshit
13 | R2R | CHS4_C_879 | Fixed asset - Master data | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_879_Asset_MD_ |  |  | Binoj/Harshit
14 | R2R | CHS4_C_880 | CO - Internal order | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_880_Internal order_M0D |  |  | Binoj/Harshit
15 | R2R | CHS4_C_881 | Customer - extend existing record by credit management data | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | In Progress |  | DMC | PRJ_R2R_CHS4_C_881_Customer_extend |  |  | Binoj/Harshit
16 | MD | CHS4_C_882 | Sites and DCs | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | Not Started |  | LSMW | PRJ_RET_CHS4_C_882_Site_DC |  |  | Vishnu
17 | MD | CHS4_C_883 | Characteristic | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | Not Started |  | DMC | PRJ_RET_CHS4_C_883_Characteristic_M10 |  |  | Vishnu
18 | MD | CHS4_C_884 | Class | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | On Hold |  | Manual (Punch In) | PRJ_RET_CHS4_C_884_Class_M11 |  |  | Vishnu
19 | MD | CHS4_C_885 | Merchandise Hierarchy | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | On Hold |  | N/A | PRJ_RET_CHS4_C_885_Merchandise Hierarchy_M12 |  |  | Koustubh
20 | MD | CHS4_C_886 | Material Group | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | On Hold |  | DMC | PRJ_RET_CHS4_C_886_Merchandise Catergories_M13 |  |  | Koustubh
21 | MD | CHS4_C_887 | Material Master | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | Not Started |  | PLM/DMC | PRJ_RET_CHS4_C_887_Materials_M14 |  |  | Koustubh
22 | MD | CHS4_C_888 | Material Master - extend existing record by new org levels | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | Not Started |  | PLM/DMC | PRJ_RET_CHS4_C_888_Materials_ext_M15 |  |  | Koustubh
23 | MD | CHS4_C_889 | Product consumption | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | Not Started |  | N/A | PRJ_RET_CHS4_C_889_Product_consumption_M16 |  |  | Koustubh
24 | MD | CHS4_C_890 | Service product | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | Completed |  | N/A | PRJ_RET_CHS4_C_890_Service_product_M17 |  |  | Koustubh
25 | O2C | CHS4_C_891 | Condition record for pricing (general template) | InScope |  |  |  |  | Awaiting Load File | Anu | [6 empty] | 0 | Completed |  | DMC | PRJ_O2C_CHS4_C_891_Con_pricing_M18 |  |  | Sarah
26 | O2C | CHS4_C_892 | Condition record for pricing in sales (restricted) | InScope |  |  |  |  | Awaiting Load File | Anu | [6 empty] | 0 | Completed |  | DMC | PRJ_O2C_CHS4_C_892_Con_pricing_res_M19 |  |  | Sarah
27 | RET | CHS4_C_893 | Customer | InScope |  |  |  |  | Awaiting Load File | Anu | [6 empty] | 0 | Completed |  | DMC | PRJ_MD_CHS4_C_893_Customer_M1A |  |  | Xiao Fu
28 | RET | CHS4_C_894 | Customer - extend existing record by multiple addresses | InScope |  |  |  |  | Awaiting Load File | Anu | [6 empty] | 0 | Completed |  | DMC | PRJ_MD_CHS4_C_894_Customer_EXT_Addrss |  |  | Xiao Fu
29 | RET | CHS4_C_895 | Customer - extend existing record by new org levels | InScope |  |  |  |  | Awaiting Load File | Anu | [6 empty] | 0 | Completed |  | DMC | PRJ_MD_CHS4_C_895_Customer_EXT_ORG_M1B |  |  | Xiao Fu
30 | O2C | CHS4_C_896 | Material listing and exclusion | InScope |  |  |  |  | Awaiting Load File | Anu | [6 empty] | 0 | Completed |  | PLM/DMC | PRJ_O2C_CHS4_C_896_Material_listingexclusion_M1C |  |  | Sarah
31 | O2C | CHS4_C_897 | SD - Sales contract | InScope |  |  |  |  | Awaiting Load File | Anu | [6 empty] | 0 | Not Started |  | DMC | PRJ_O2C_CHS4_C_897_Sales contract_M1D |  |  | Sarah
32 | O2C | CHS4_C_898 | SD - Sales order (only open SO) (SD Sales orders - VAS records and conditions) | InScope |  |  |  |  | Awaiting Load File | Anu | [6 empty] | 0 | Not Started |  | DMC | PRJ_O2C_CHS4_C_898_Sales Order_M1E |  |  | Sarah
33 | RET | CHS4_C_899 | Supplier | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | DMC | PRJ_MD_CHS4_C_899_Supplier_M0H |  |  | Xiao Fu
34 | RET | CHS4_C_900 | Supplier - extend existing record by multiple addresses | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | DMC | PRJ_MD_CHS4_C_900_Supplier_Ext_address |  |  | Xiao Fu
35 | RET | CHS4_C_901 | Supplier - extend existing record by new org levels | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | DMC | PRJ_MD_CHS4_C_901_Supplier_Ext_M0J |  |  | Xiao Fu
36 | P2P | CHS4_C_902 | MM - Purchasing info record with conditions | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | DMC | PRJ_P2P_CHS4_C_902_PIR_M0K |  |  | Koustubh
37 | P2P | CHS4_C_903 | Condition record for pricing in purchasing (restricted) | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | PLM/DMC | PRJ_P2P_CHS4_C_903_Condition_Price_purchase_M0L |  |  | Koustubh
38 | P2P | CHS4_C_904 | Material - Forecast planning | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | N/A | PRJ_P2P_CHS4_C_904_Material_ Forecast_ planning_M03 |  |  | Koustubh
39 | P2P | CHS4_C_905 | Material inventory balance | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | PLM/DMC | PRJ_P2P_CHS4_C_905_Material_inventory_balance_M0N |  |  | Koustubh
40 | P2P | CHS4_C_907 | MM - Purchase order (only open PO) | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | DMC | PRJ_P2P_CHS4_C_907_Purchase_order _M0G |  |  | Koustubh
41 | P2P | CHS4_C_909 | MM - Source list | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | DMC | PRJ_P2P_CHS4_C_909_Source list_M0O |  |  | Koustubh
42 | P2P | CHS4_C_910 | Batch unique at material and client level | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | N/A | PRJ_P2P_CHS4_C_910_Batch_Material_M0P |  |  | Koustubh
43 | P2P | CHS4_C_911 | Batch unique at plant level | InScope |  |  |  |  | Awaiting Load File | Sharon | [6 empty] | 0 | Not Started |  | N/A | PRJ_P2P_CHS4_C_911_Batch_Plant_M0Q |  |  | Koustubh
44 | R2R | CHS4_C_926 | Good Will Impairment Analysis | InScope |  |  |  |  | Awaiting Load File | Manoj | [6 empty] | 0 | Not Started |  | Manual (Punch In) | N/A |  |  | Binoj/Harshit
45 | MD | CHS4_C_927 | Classification | InScope |  |  |  |  | Awaiting Load File | Sona | [6 empty] | 0 | Not Started |  | Manual | TBD |  |  | Vishnu
46 | R2R |  | Exchange Rates - Manual | InScope |  |  |  |  | Awaiting Load File | [7 empty] | 0 | Not Started |  | Manual
47 | R2R |  | ALL - TVARVC entries | InScope |  |  |  |  | Awaiting Load File | [7 empty] | 0 | Not Started |  | Manual
48 | R2R |  | Cost Center Hierarchy - Manual | InScope |  |  |  |  | Awaiting Load File | [7 empty] | 0 | Not Started |  | Manual
49 | R2R |  | PC Hierarchy - Manual | InScope |  |  |  | 2025-08-15 | Awaiting Load File | [7 empty] | 0 | Not Started |  | Manual
Note on V17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Site creation using LSMW
Note on D46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New object confirmed by Vishnu

## CustomTable
ZCA_RICEF_ATRBTS
ZCA_TXT_TRANSLTE
ZLAB_CODES
ZLAB_EXCPT
ZLIQUID
ZMM_GRIDTYPES
ZMM_MATERIALGRID
ZMM_PURCHASEGRID
ZMM_SALESGRID
ZPHASE
ZPLM_UPC
ZRET_EMP_MASTER
ZRET_POXREF
ZRET_PO_AGE_XREF
ZRET_SIZECODES
ZRET_S_SIZECODES
ZRET_S_SIZECODES_R
ZRET_TAXGRP_MAP
ZSIZECODES
ZUPCXREF

## GP Pivot Table
DM Scope | InScope
Load Method | (All)
Count of WorkStream |  | Extract Program Status
WorkStream | Planned Loading Date | Complete | (blank) | N/A | Grand Total
MD |  | 6 | 2 |  | 8
OTC |  | 1 | 6 | 1 | 8
P2P |  | 4 | 7 | 4 | 15
R2R |  | 5 | 9 | 2 | 16
RET |  |  | 9 |  | 9
Grand Total |  | 16 | 33 | 7 | 56